CONTRACT MODIFICATION PROCEDURES

# PART 1 - GENERAL

1.1	SUMMARY

A.	This Section specifies administrative and procedural requirements for making modifications to the contract including:

1.	Change Orders

2.	Construction Change Documents (see General Conditions)

3.	Contract Credits

4.	Contract Additions

5.	Construction Change Directives

6.	Immediate Change Directives (see General Conditions)

7.	Instructions

B.	Modifications:

1.	Provide full written data required to evaluate contract modifications, including breakdown of labor, material, equipment and description of work with unit costs for each category.

2.	Maintain detailed records of work done on a time-and-material basis.

3.	Provide full documentation for all proposed Change Orders to the Architect for his review.

C.	Designate in writing the member of Contractor's organization:

1.	Who is authorized to accept changes in the Work.

2.	Who is responsible for informing others in the Contractor's employ of the authorization of changes in the Work.

1.2	RELATED SECTIONS

A.	Addenda: All issued Addendums

B.	Agreement:  The amounts of unit prices if any as established in the Contract.

C.	General Conditions Article 7, Changes in the Work.

D.	Section 01330 - Submittals

E.	Section 01630 - Product Substitution Procedures

1.3	REFERENCES

A.	Change Order Requirements per Title 24 Part 1 CCR.

1.	Changes in the plans and specifications are to be made by addenda or Change Orders or construction change documents approved by the Division of the State Architect, Title 24 Part 1 Section 4-338.

2.	Change Orders: Changes or alterations of the approved plans or specifications after a contract for the work has been awarded are to be made by means of Change Orders. State the reason for the change and provide supplementary drawings where necessary. Change Orders must be manually signed by the Architect or Engineer in general responsible charge of observation of the work or by the Architect or Engineer delegated responsibility for observation of the portion of the work affected by the Change Order.

3.	Change Orders are required to bear the approval of the School Board or their authorized representative upon delegated authority.

4.	One original signed copy by all parties of each Change Order is required for the files of the Division of the State Architect.

1.4	PRELIMINARY PROCEDURES

A.	The Architect or School District may initiate changes by submitting a Request For Proposal.  The request will include:

1.	Detailed description of the Change, Products, and location of the change in the Project. Changes may include additions and deletions from the Contract.

2.	Supplementary or revised Drawings and Specifications.

3.	The projected time span for making the change and a specific statement as to whether overtime work is, or is not, authorized.

4.	A specific period of time during which the requested price will be considered valid.

5.	Such request is for information only, and is not an instruction to execute the changes, nor to stop Work in progress.

B.	Contractor may initiate changes by submitting a written Change Order Request to the Architect or School District containing:

1.	Description of the proposed change.

2.	Statement of the reason for making the changes.

3.	Statement of the effect on the Contract Sum/ Contract Price and the Contract Time.

4.	Statement of the effect on the Work of separate contractors with breakdown of costs for labor, materials and equipment.

5.	Documentation supporting any change in Contract Sum/ Contract Price or Contract Time, as appropriate.

1.5	CONSTRUCTION CHANGE DIRECTIVES

A.	In lieu of Proposal Request, the School District through the Construction Manager may issue, a Construction Change Directive (also referred to as an Immediate Change Directive in the General Conditions) for Contractor to proceed with a change which shall state a basis for adjustment, if any, in the Contract Sum/ Contract Price or Contract Time, or both.

B.	Authorization will describe changes in the Work, both additions and deletions, with attachments of revised Contract Documents to define details of the change, and will designate the method of determining any change in the Contract Sum/ Contract Price and any change in Contract Time.

C.	The School District and Architect will sign and date the Construction Change Directive as authorization for the Contractor to proceed with the changes.

D.	Contractor may sign and date the Construction Change Directive to indicate agreement with the terms therein.

1.6	DOCUMENTATION OF PROPOSALS AND CLAIMS

A.	Support each quotation for a lump-sum proposal, and for each unit price which has not previously been established, with sufficient substantiating data to allow the Engineer and School District to evaluate the quotation.

B.	On request provide additional data to support time and cost computations:

1.	Labor required in hours with unit costs.

2.	Equipment required.

3.	Products required in units.

a.	Recommended source of purchase and unit cost.

b.	Quantities required.

4.	Taxes, insurance and bonds.

5.	Credit for Work deleted from Contract, similarly documented.

6.	Overhead and profit.

7.	Justification for any change in Contract Time.

C.	Support each claim for additional costs, and for work done on a time and material basis, with documentation as required for a lump-sum proposal, plus additional information:

1.	Name of the School District's authorized agent who ordered the work, and date of the order.

2.	Dates and times work was performed, and by whom.

3.	Time record, summary of hours worked, and hourly rates paid.

4.	Receipts and invoices for:

a.	Equipment used, listing dates and times of use.

b.	Products used, listing of quantities.

c.	Subcontracts.

D.	Document requests for Substitution of Products as specified in Section 01630.

1.7	CONSTRUCTION CREDITS

A.	Work deleted and no work has been completed by the Contractor:  Work deleted from the contract is to be credited back to the District and subtracted from the contract amount. Credits are to be included in Change Orders.

1.	Contractor shall credit back to the District total value for the work deleted from the contract. Cost of credits shall be determined by the amount stated in the Contractor's Schedule of Values.

2.	Where the value of credits cannot be determined from the Contractor's Schedule of values, total value of the credit is to be determined by the cost of materials, labor, overhead and profit, insurance, bonds, etc. All General Contractor, Subcontractor and Material Supplier levels of the Contract are to be included in the total value of credits back.

3.	No amount at any level of the contract shall be withheld from credits for overhead and profit, insurance, bonds, time delays, construction schedule changes and administrative expenses.

B.	Work deleted and a portion of the work has been completed by the Contractor:  Work deleted from the contract is to be credited back to the District and subtracted from the contract amount. Credits are to be included in Change Orders.

1.	Contractor shall credit back to the District the total value of the work deleted from the contract less any work already completed on the credit item. Cost of credits shall be determined by the amount stated in the Contractor's Schedule of Values less any work already completed. Completed work may include cost of shop drawings, submittals, site preparation, partially completed work on the credit item or other expenses related to the item.

2.	Where the value of credits cannot be determined from the Contractor's Schedule of values, total value of the credit is to be determined by the cost of materials, labor, overhead and profit, insurance, bonds, etc. All General Contractor, Subcontractor and Material Supplier levels of the Contract are to be included in the total value of credits back.

3.	An amount equal to the percentage of work already completed on the deleted item may be withheld from credits back for overhead and profit, insurance, bonds, construction schedule adjustments and administrative expenses, as indicated in the General Conditions (Section 00700).

1.8	PREPARATION OF CHANGE ORDERS

A.	The Architect will prepare each Change Order.

B.	Change Order will describe changes in the Work, both additions and deletions, with attachments of revised Contract Documents to define details of the change.

C.	Change Order will provide an accounting of the adjustment in the Contract Sum/ Contract Price and in the Contract Time.

1.9	LUMP-SUM/FIXED PRICE CHANGE ORDER

A.	Content of Change Orders will be based on either:

1.	The School District's Proposal Request and Contractor's responsive Proposal as mutually agreed with the School District.

2.	Contractor's Proposal for a change, as recommended by the School District or their authorized agent.

B.	The School District, Division of the State Architect and Architect or Engineer in responsible charge will sign and date the Change Order as an authorization for the Contractor to proceed with the changes.

C.	The Contractor will sign and date the Change Order to indicate agreement with the terms therein.

1.10	UNIT PRICE CHANGE ORDER

A.	Content of Change Orders will be based on either:

1.	The School District's definition of the scope of the required changes.

2.	Contractor's Proposal for a change, as recommended by the School District or Authorized Agent.

3.	Survey of completed work.

B.	The amounts of the unit prices to be:

1.	Those stated in the Agreement.

2.	Those mutually agreed upon between School District and Contractor.

C.	When quantities of each of the items affected by the Change Order can be determined prior to start of the work:

1.	The School District and Architect or Engineer in responsible charge will sign and date the Change Order as authorization for Contractor to proceed with the changes.

2.	Contractor is to sign and date the Change Order to indicate agreement with the terms therein.

D.	When quantities of the items cannot be determined prior to start of the work:

1.	The School District through the Architect will issue a Construction Change Directive directing the Contractor to proceed with the change on the basis of unit prices, and will cite the applicable unit prices.

2.	At completion of the change, the School District or its authorized agent will determine the cost of such work based on the unit prices and quantities used.

3.	The Contractor shall submit documentation to establish the number of units of each item and any claims for a change in Contract Time.

4.	The School District, Division of the State Architect and Architect or Engineer in responsible charge will sign and date the Change Order as authorization for the Contractor to proceed with the Changes.

5.	The Contractor will sign and date the Change Order to indicate agreement with the terms therein.

1.11	TIME AND MATERIALS CHANGE ORDER/CONSTRUCTION CHANGE DIRECTIVE:

A.	The School District through the Architect will issue a Construction Change Directive directing Contractor to proceed with the changes

B.	At completion of the change, Contractor shall submit itemized accounting and supporting data as provided in the Article 1.6, "Documentation of Proposals and Claims," of this Section.

C.	The School District or its authorized representative will determine the allowable cost of such work, as provided in General Conditions and Supplementary Conditions.

D.	The School District, Division of the State Architect and Architect or Engineer in general responsible charge will sign and date the Change Order to authorize the change in Contract Sum/ Contract Price and in Contract Time.

E.	The Contractor will sign and date the Change Order to indicate agreement with the terms therewith.

1.12	INSTRUCTIONS

A.	Architect's Supplemental Instructions:

1.	Minor changes in the work shall be carried out in accordance with supplemental instructions issued in accordance with the Contract Documents without change in Contract Sum/ Contract Price or Contract Time.

2.	The Architect will issue, sign, and date Supplemental Instructions.

3.	The Contractor will sign and date Supplemental Instructions to indicate acceptance of minor changes consistent with the Contract Documents and return signed copy to Architect.

1.13	CORRELATION WITH CONTRACTOR'S SUBMITTALS

A.	Periodically revise Schedule of Values and Request for Payment forms to record each change as a separate item of Work and to record the adjusted contract amounts.

B.	Periodically revise the Construction Schedule to reflect each change in Contract Time.

C.	Revise sub-schedules to show changes for other items of work affected by the changes.

D.	Upon completion of work under a Change Order, enter pertinent changes in Record Documents.

1.14	FORMS

A.	Submit Proposal Request typed on AIA Document G709. A Copy of this form may be obtained from the local American Institute of Architects, Chapter Office

B.	Submit Change Orders typed on the Change Order Form included in this Project Manual.  Form is included in General Conditions and at the end of this Section.

C.	Submit Construction Change Directive on the Construction Change Directive Form included in this Project Manual.  Form is included in General Conditions and at the end of this Section

D.	Submit Supplemental Instructions typed on the form included in this Project Manual at the end of Document 00935, Requests For Interpretation (RFI's).

E.	Immediate Change Directive Form is included in the Supplementary General Conditions.

PART 2 – PRODUCTS - (Not Applicable)

PART 3 – EXECUTION - (Not Applicable)

### END OF SECTION