COMPTON COMMUNITY COLLEGE DISTRICT

1111 E. Artesia Blvd

Compton, California 90221

(310) 900-1600

Bid Pack #01	Project Number: CCCD-026

GENERAL CONDITIONS

## TABLE OF CONTENTS

Article 1  PURPOSE OF THESE GENERAL CONDITIONS	8

Article 2  DEFINITIONS	8

2.1	Applicable Laws	8

2.2	Construction Manager	8

2.3	Construction Schedule	8

2.4	Contract Price	8

2.5	Contractual Completion Date	8

2.6	DSA	8

  - Hazardous Materials	9

  - Hazardous Material Laws	9

  - Inspector	9

  - Notice of Award	9

  - Notice to Proceed	9

  - OCIP	9

  - Price Contractor	9

  - Subcontractor	9

  - Work	9

  - Work Activity	10

Article 3  RELATIONSHIP OF PARTIES	10

3.1	Architect	10

3.2	Inspectors	11

3.3	Contractor	12

3.4	Subcontractors	12

3.5	Construction Manager	14

Article 4  INTERPRETATION AND RELATIONSHIP OF DOCUMENTS	15

4.1	Intent of the Project Documents	15

4.2	Purpose of Plans vs. Purpose of Specifications	15

4.3	Organization of the Plans and Specifications	15

4.4	Questions Regarding Perceived Inconsistencies	16

4.5	Effect of Inconsistencies as to Quality or Quantity	16

4.6	Order of Priority Among Conflicting Project Documents	16

4.7	Conflicts Within the Plans	17

4.8	Conflicts Within the Specifications	17

4.9	Conflicts Between Project Documents and Other Documents or Applicable Laws	17

4.10	Omissions	17

4.11	References to Trade Names	18

4.12	Named Materials and Equipment Must Be Furnished and Installed	18

4.13	Substituted Items	18

4.14	Detail Drawings and Instructions	18

4.15	Ownership of Drawings	19

4.16	Other Contracts	19

Article 5  CONSTRUCTION SCHEDULE	19

5.1	Commencement, Performance and Completion of Work	19

5.2	Preparation of Initial Construction Schedule Upon District’s Notice to Proceed	20

5.3	Work Activities Reflected in Construction Schedule	20

5.4	Float	20

5.5	District’s Approval of Initial Construction Schedule	21

5.6	Effect of Change Orders	21

5.7	Weekly Reports	21

5.8	Monthly Updates	21

5.9	Additional Revisions Requested by District	23

5.10	Contractor’s Failure to Adhere to Construction Schedule	23

5.11	Limitation on Time Extensions and Delay Damages	24

Article 6  CONTRACTOR’S OBLIGATIONS PRIOR TO COMMENCEMENT OF WORK	24

6.1	Knowledge of and Compliance with Applicable Laws	24

6.2	Examination of Project Documents	25

6.3	Site Investigation	25

6.4	Contractor Shall Inspect for Defects in Existing Work	25

6.5	Soils Investigations and Reports	26

6.6	Layout and Field Engineering	26

6.7	Field Measurements and Verification of Dimensions	26

6.8	Surveys	27

6.9	Appointment of Contractor’s Superintendent	27

6.10	Permits, Licenses, Approvals and Certificates	27

6.11	Insurance	28

Article 7  MANNER IN WHICH WORK IS TO BE PERFORMED	28

7.1	Contractor’s Supervision of Work	28

7.2	Performance of Work in Violation of Applicable Laws	28

7.3	Materials and Work	28

7.4	Integration of Work	29

7.5	Coordination With Other Work	30

7.6	Tests and Inspections	30

7.7	Trenches	30

7.8	Removal and Restoration of Existing Utility Lines	31

7.9	Minimizing Interference with School Operations	32

7.10	Protection of Persons and Property	32

7.11	Utilities and Facilities at Project Site	34

7.12	Sound and Noise Controls	35

7.13	Emission Controls	35

7.14	Archeological Artifacts	35

7.15	Cleanup of Project and Work Site	35

7.16	Payments by Contractor	35

7.17	Liens and Lien Releases	36

7.18	District’s Access to Work	37

7.19	District’s Right to Perform Work	37

Article 8  COMPLETION OF WORK	38

8.1	Finished Work	38

8.2	Walk-Through As Prerequisite to Determination of Completion	38

8.3	District’s Acceptance of Work	38

8.4	Notice of Completion	38

8.5	Contractor’s Failure to Correct Punch-List Items	38

8.6	Rejection and Correction of Work	38

Article 9  WAGES, HOURS AND WORK FORCE	39

9.1	Contractor to Supply Sufficient Workforce	39

9.2	Duty to Provide Fit Workers	39

9.3	Prevailing Wages	39

9.4	Apprentices	41

9.5	Hours of Work	42

9.6	Provision of First Aid to Workers	43

Article 10  DOCUMENTATION	43

10.1	Documentation of Work	43

10.2	District’s Audit Rights	43

10.3	Drawings Reflecting Actual Construction	45

10.4	Records Related to Change Orders	45

10.5	Payroll Records	46

Article 11  HAZARDOUS MATERIALS, ASBESTOS, AND DIFFERING CONDITIONS	47

11.1	Hazardous Materials	47

11.2	Asbestos	48

11.3	Discovery of Hazardous Materials	49

11.4	Discovery of Differing Conditions	49

11.5	District’s Investigation of Contractor’s Report of Hazardous Materials or Differing Conditions	49

11.6	Material Safety Data Sheets (MSDS)	49

Article 12  SHOP DRAWINGS	50

12.1	Overview of Shop Drawing Procedures	50

12.2	Shop Drawings Shall Conform to Plans and Specifications	50

12.3	Definition of “Shop Drawings”	50

12.4	Transmittal Form	50

12.5	Material and Equipment Suppliers	51

12.6	Contractor’s Stamp Approving Shop Drawings	51

12.7	Architect’s Review of Shop Drawings	51

12.8	Contractor’s Re-Submittal of Shop Drawings	51

12.9	No Work or Fabrication If Shop Drawings Must Still Be Resubmitted	52

12.10	Revisions on Shop Drawings Are Not Grounds for Claims for Extra Work	52

12.11	Simultaneous Submission of Related Shop Drawings	52

12.12	DSA Approval of Shop Drawings and Deferred Approval Items	52

12.13	Limitation on Contractor’s Claims Relative to Shop Drawings	52

Article 13  SAMPLES	52

13.1	Contractor’s Duty to Provide Samples	52

13.2	Standards	53

13.3	Testing	53

Article 14  CONTRACT TIME	53

14.1	Commencement and Completion Dates	53

14.2	Adjustment Of Completion Date Due to Unforeseeable or Uncontrollable Acts	53

14.3	No Adjustment Based on Normal Weather or Industrial Conditions	54

14.4	Delays Caused by District or Architect	54

14.5	Substantiation of Delay	54

14.6	Liquidated Damages	54

14.7	Time is of the Essence	54

Article 15  REQUESTS FOR INFORMATION	54

15.1	Architect’s Response to Requests for Interpretation, Clarification or Instructions	54

15.2	Procedure Where Contractor Believes a Response to a Request for Information Expands the Scope of Work	55

15.3	Improper Requests for Information	53

Article 16  CHANGES TO THE WORK	56

16.1	Change Orders in General	56

16.2	Proposed Change Orders	56

16.3	Allowable Costs In Connection With Change Orders	58

16.4	Failure to Agree as to Cost for Added Work	62

16.5	Failure to Agree as to Cost for Deleted Work	63

16.6	Allowable Time Extensions	63

Article 17  BONDS	66

Article 18  INSURANCE	66

18.1	Inapplicability of This Article if Project is Subject to OCIP	66

18.2	Fire Insurance	66

18.3	Commercial General Liability and Property Damage Insurance	66

18.4	Workers’ Compensation Insurance	67

18.5	Proof of Insurance	67

18.6	District May Obtain Insurance at Contractor’s Expense	68

Article 19  CLAIMS AND DAMAGES	69

19.1	Claims Procedures	69

19.2	Contractor’s Duty to Perform Work Pending Resolution of Dispute	70

19.3	Claims of $375,000 or Less	70

19.4	Claims Above $375,000	70

19.5	Architect’s Written Decision	70

19.6	Continuing Contract Performance	70

19.7	Claims for Concealed Trenches or Excavations Greater Than Four Feet Below the Surface	70

19.8	Claims for Extension of Time	71

19.9	Claims Procedures	71

19.10	Binding Arbitration of Individual Claim Issues	73

19.11	Resolution of Disputes in Court of Competent Jurisdiction	73

19.12	Warranties, Guarantees and Obligations	74

Article 20  WARRANTY OF WORK	74

20.1	Warranty as to Condition of Work	74

20.2	Warranty Period	74

20.3	Correction of Defective Work	74

20.4	District’s Right to Correct Defects	74

20.5	Limitation on Notice Requirements	75

20.6	No Effect on Other Guarantees	75

20.7	Form of Guaranty	75

20.8	Instruction Manuals	75

20.9	No Limitation on District’s Other Rights	75

20.10	Attorneys’ Fees	75

Article 21  PAYMENTS TO CONTRACTOR	75

21.1	Cost Breakdown and Periodic Estimates	75

21.2	Monthly Payments by the District to the Contractor	76

21.3	Schedule of Values	76

21.4	Monthly Payment Requests	76

21.5	Partial Payments; Retention	77

21.6	Information Required from Contractor	77

21.7	Contractor’s Certificate	77

21.8	Final Payment	78

21.9	Adjustments to Contract Price	78

21.10	Payments Withheld in Addition to Retention Amounts	78

21.11	Reimbursable Expenses	79

Article 22  DISTRICT’S RIGHT TO TERMINATE AGREEMENT	80

22.1	Termination by the Contractor for Cause	80

22.2	Termination by the District for Cause	80

22.3	Notification of Termination	80

22.4	Payments Withheld	81

22.5	Payments Upon Completion	81

22.6	Termination of Contract by District (Contractor Not At Fault)	81

22.7	Non-Appropriation of Funds / Insufficient Funds	81

22.8	Remedies Other Than Termination	82

Article 23  MISCELLANEOUS	83

23.1	Prohibited Interests	83

23.2	Notice of Taxable Possessory Interest	83

23.3	Assignment of Antitrust Actions	83

23.4	Occupancy	83

23.5	Patents, Royalties and Indemnities	84

23.6	Non-Discrimination	84

23.7	Excise Taxes	84

23.8	No Assignment	84

23.9	Notice	84

23.10	No Waiver	85

23.11	No Oral Agreements	85

23.12	Time is of the Essence	85

23.13	Indeminfication	85

GENERAL CONDITIONS

- PURPOSE OF THESE GENERAL CONDITIONS

These General Conditions (“General Conditions”) contain general terms and conditions which are applicable to that certain construction agreement (“Agreement”) that has been or will be entered into by Compton Community College District (the “District”) and the contractor identified therein (the ”Contractor”) in connection with the District’s construction project identified by the Project Number listed on the title page of these General Conditions (the “Project”).

- DEFINITIONS

Except as otherwise defined in these General Conditions, all capitalized terms contained in these General Conditions shall mean those terms as they are defined in the following documents: (a) the Agreement; (b) the Notice Calling for Bids issued by the District in connection with the Project (the “Notice Calling for Bids”); (c) the Information for Bidders issued by the District in connection with the Project (the “Information for Bidders”); and (d) all of the other Project Documents identified in the Information for Bidders (collectively, the “Project Documents”).  In addition, the following terms shall have the following meanings in these General Conditions:

  - “Applicable Laws” shall have the meaning set forth in Section 6.1 below.

  - “Construction Manager” means a person or entity retained by the District in connection with the Project to oversee the Contractor’s performance of its obligations under the Agreement and the other Project Documents.

  - “Construction Schedule” means a schedule of the anticipated progress of the Work, to be prepared by the Contractor and approved by the District pursuant to the provisions of Article 5 of these General Conditions.

  - “Contract Price” means the amount payable to the Contractor under the Agreement.

  - “Contractual Completion Date” means the date specified in Section 4 of the Agreement for the completion of the Work.

  - “DSA” means the California Department of General Services’ Division of the State Architect.

  - “Hazardous Materials” shall have the meaning set forth in Section 11.1 below.

  - “Hazardous Material Laws” means any applicable federal, state or local laws, ordinances, or regulations relating to any Hazardous Material affecting the Property, including, without limitation, the laws, ordinances, and regulations referred to in Section 11.1 below.

  - “Inspector” means a person or entity retained by the District for the purpose of inspecting the quality of the Work to determine whether that Work conforms to the requirements of the Plans and Specifications and other Project Documents.

  - “Notice of Award” means written notice from the District to the Contractor advising the Contractor that the District’s Board of Education has accepted the Contractor’s bid.  The Notice of Award may be conditioned upon the Contractor’s provision of documents or performance of acts identified in the Notice of Award.

  - “Notice to Proceed” means written notice from the District to the Contractor instructing the Contractor to proceed with the Work.

  - “OCIP” means any Owner Controlled Insurance Program in which the District participates.

  - “Prime Contractor” means a contractor on the Project who has responsibility for one or more trades or crafts necessary to the construction of the Project, and who has entered into a direct contractual relationship with the District (as opposed to a subcontractor of a general contractor or other third party).  Although Prime Contractors are not referenced elsewhere in these General Conditions, Prime Contractors may be identified in other Project Documents if the District has elected to use a “multi-prime” delivery method for the Project by entering into numerous separate “prime” contracts with various Prime Contractors for construction of separate aspects of the Work, rather than entering into only one “general” contract with one general contractor for all of the Work.  In such a case, all references to “Contractor” herein shall be deemed references to the Prime Contractor who is a party to the prime contract, which constitutes the  Agreement.

  - “Subcontractor” means any person or entity having a direct contractual relationship with the Contractor and who furnishes labor or services as part of the Work on the Project.  The term “Subcontractor” does not include a person or entity who merely provides material, supplies, equipment or appliances, but who does not design or alter same to meet the Plans or Specifications or who does not install the material, supplies, equipment or appliances, otherwise provide labor according to plans, drawings, and specifications of the Work.

  - “Work” means the performance of any labor or other services performed for the Project, or the provision of any materials, supplies, equipment, appliances or other items in connection with the Project, by the Contractor or by any Subcontractor.  Without limiting the generality of the foregoing, “Work” includes all materials, supplies, equipment and appliances which have been incorporated into the construction contemplated by the Project Documents or delivered to the Project site for incorporation into such construction.

  - “Work Activity” means an activity, which requires time and resources (including manpower, equipment, or material) to complete.  Work Activities shall include, but not be limited to: mobilization; submittals; Architect’s review of each submittal; procurement, delivery installation and checkout of equipment or material; Subcontractor’s items of Work; and all major construction activities.

- RELATIONSHIP OF PARTIES

  - Architect.  The Architect shall observe the progress and quality of the Work on behalf of the District.

    - Architect’s Authority.  The Architect has the authority to enforce compliance with the Project Documents, and is otherwise authorized to act on behalf of the District relative to the Project, but only to the extent expressly provided in the Project Documents.  Without limiting the generality of the foregoing, the Architect shall have the authority to do all of the following:

      - Determination of Satisfactory Performance.  To determine the acceptability of Work and/or of the Contractor’s performance under the Agreement and the other Project Documents, including without limitation rendering decisions on behalf of the District as to (i) the quantity or quality of materials or equipment, (ii) the acceptability of such materials or equipment or of any workmanship or services, or (iii) the execution, progress or sequence of any Work;

      - Interpretation of Plans and Specifications.  To interpret Plans, Specifications, and other drawings relative to the Project;

      - Authority to Stop Work.  To stop the Work whenever such stoppage may be necessary in the Architect’s reasonable opinion to ensure the proper execution of the Project Documents;

      - Authority to Enforce Contractor’s Performance.  To enforce the Contractor’s faithful performance of the Contractor’s obligations under the Agreement and the other Project Documents; and

      - Authority Established by Law.  To exercise any and all other authority and responsibility established by law, including without limitation Title 24 of the California Code of Regulations.

    - Contractor to Comply with Architect’s Instructions.  The Contractor shall promptly comply with instructions from the Architect (which shall be delivered by the Construction Manager identified in Section 3.5 below if one has been appointed by the District) relative to compliance with Project Documents and relative to any other matter as to which the Architect has authority pursuant to the Project Documents.  If the Contractor fails to do so, the District shall have the right to suspend payments otherwise owing to the Contractor under the Project Documents until the Architect has notified the District of the Contractor’s compliance.  The Contractor shall not delay or otherwise impair the progress or completion of the Work, even if payments to the Contractor are suspended hereunder or even if the Contractor otherwise disagrees with any of the Architect’s instructions or decisions.

    - Architect’s Activities Do Not Relieve Contractor of its Obligations.  General supervision and direction of the work by the Architect shall not imply that the Architect or the District are in any way responsible for the safety of the Contractor, Subcontractors or their employees, shall not imply that the Architect or the District will maintain supervision over the Contractor’s construction methods or personnel, and shall not relieve the Contractor of any of its obligations under the Project Documents.

  - Inspectors.

    - District’s Use of Inspectors.  One or more Inspectors, including special inspectors, as required, will be employed or otherwise retained by the District in accordance with requirements of Title 24 of the California Code of Regulations and will be assigned to the Project.  Each such Inspector shall have such rights and duties relative to the Project as shall be established by the District, including without limitation those set forth in Section 4-342 of Title 24 of the California Code of Regulations.

    - Contractor’s Duties Relative to the Inspection.  Neither the Contractor nor any of its Subcontractors shall perform any Work except with the knowledge and under the inspection of the Inspector(s).  Each Inspector shall have free access to any or all parts of the Work at any and all times.  The Contractor shall furnish each Inspector reasonable opportunities for obtaining such information as may be necessary to keep the Inspector fully informed as to all aspects of the Work.

    - Inspector’s Right to Stop Work.  The Inspector shall have authority to stop the Work whenever the Inspector discovers that the Work is not being conducted in accordance with the provisions of Project Documents.  The Contractor shall instruct its employees accordingly.  Nothing in this paragraph is intended to limit the rights of the Architect or the Construction Manager to stop the Work pursuant to Section Article 3(c) above and 3.5.3 below.

    - Limitation on Inspector’s Authority.  No Work shall be performed by the Contractor solely upon the instructions or comments by the Inspector.  The Inspector has no authority to interpret the Project Documents or order extra Work.  Any extra work performed without the written instruction of the District shall be at Contractor’s sole cost and expense and there will be no delay damages incurred by the District for such work.

    - Inspector’s Activities Do Not Relieve Contractor of its Obligations.  The Inspector’s inspection of the Work shall not imply that the Inspector or the District is in any way responsible for the safety of the Contractor, Subcontractors or their employees, shall not imply that the Inspector or the District will maintain supervision over the Contractor’s construction methods or personnel, and shall not relieve the Contractor of any of its obligations under the Project Documents.

  - Contractor.

    - The Contractor is an Independent Contractor.  The Contractor is and shall at all times be deemed to be an independent contractor.  The Contractor shall be wholly and solely responsible for and have control over the manner in which it performs the services required of it by the terms of the Project Documents, including without limitation construction means, methods, techniques, sequences, procedures, safety precautions, furnishing of equipment and materials, and coordination of all portions of the Work.  Nothing herein contained shall be construed as creating the relationship of employer and employee, or principal and agent, between the District and the Contractor or any of the Contractor’s agents or employees.  The Contractor assumes exclusively the responsibility for the acts of its employees as they relate to the services to be provided during the course and scope of their employment.  The Contractor, its agents and employees shall not be entitled to any rights or privileges of the District’s employees and shall not be considered in any manner to be the District’s employees.  The District shall be permitted to monitor the activities of the contractor to determine compliance with the terms of the Project Documents.

    - Representation as to Contractor’s License.  The Contractor represents and warrants to the District that (a) the Contractor is duly licensed by the Contractors State License Board, (b) all of the license information pertaining to the license number(s) and license class(es) contained in the Bid Form and the other Project Documents are true and correct, (c) each such license is currently in full force and effect, and (d) the Contractor has received no notice, written or otherwise, as to any pending or contemplated suspension, revocation or termination of any such license.

    - Limitations on Changes to Contractor’s Name or Entity.  The Contractor shall not change its name or its type of legal entity without first (a) notifying the District in writing of the proposed change, and (b) entering into written agreements modifying the Project Documents, to the extent requested by the District, if the District reasonably determines that modification of those Project Documents is necessary due to the change proposed by the Contractor.

  - Subcontractors.

    - Contractor is Responsible for Subcontractors’ Work.  The Contractor agrees to bind every Subcontractor by terms of the Project Documents as far as such terms are applicable to the Subcontractor’s Work.  If the Contractor shall subcontract any part of the Work, the Contractor shall be as fully responsible to the District for acts and omissions of any Subcontractor, and of persons either directly or indirectly employed by any Subcontractor, as it is for acts and omissions of persons directly employed by the Contractor.

    - No Contractual Relationship Between District and Subcontractors.  Nothing contained in Project Documents shall create any contractual relation between any Subcontractor and the District, nor shall the Project Documents be construed to be for the benefit of any Subcontractor.  The District’s consent to any Subcontractor shall not in any way relieve the Contractor of any obligations under the Project Documents, and no such consent shall be deemed to waive any provision of any of the Project Documents.

    - Coordination of Work of Subcontractors.  The Contractor shall be responsible for the coordination of the trades, Subcontractors, and material men engaged upon the Contractor’s Work.  The Contractor shall instruct all trades, Subcontractors and material men to cooperate with each other so that each can execute its Work properly.  If one or more Subcontractors disagree with each other or with the Contractor as to the interpretation of the Plans, Specifications or other Project Documents, either with respect to the obligations of the Subcontractor there under or otherwise, it shall be the Contractor’s responsibility to resolve the disagreement and to obtain or execute the performance of the Work under dispute.

    - Subletting and Subcontracting Fair Practices Act.  The Contractor represents and warrants to the District that the Contractor has complied with all of the provisions of the Subletting and Subcontracting Fair Practices Act (Public Contract Code §§ 4100 et seq.), including without limitation those referenced in Section 23 of the Information for Bidders.  The Contractor covenants that it will continue to comply with that Act throughout the duration of the Project and the term of the Project Documents.

    - Additional Requirement Where Contractor is a “Specialty Contractor”.  In accordance with Business and Professions Code § 7059, if the Contractor is designated as a “specialty contractor” (as defined in Business and Professions Code § 7058), all of the work to be performed outside of the Contractor’s license specialty shall be performed by a licensed subcontractor in compliance with the Subletting and Subcontracting Fair Practices Act.

    - Copies of Subcontracts.  A copy of each written subcontract between the Contractor and any Subcontractor (and a written statement signed by the Contractor giving the name of the Subcontractor and the terms and conditions of each such unwritten subcontract), shall be delivered to the District and the Construction Manager before the Subcontractor begins any Work.  Each subcontract shall contain a reference to the Agreement between the District and the Contractor, and the terms of that Agreement and all parts of the Project Documents shall be made a part of such subcontract insofar as applicable to the Work covered by the Subcontract.  Each subcontract will provide for termination in accordance with Article 22 of these General Conditions.  Each subcontract shall provide for its annulment by the Contractor at the order of the District if (in the opinion of the District, the Architect or the Construction Manager referenced below) the Subcontractor fails to comply with the requirements of the Project Documents insofar as the same may be applicable to the portion of the Work that is the subject of the subcontract.  Nothing herein contained shall relieve the Contractor of any liability or obligation hereunder.

  - Construction Manager.  The District may, in its discretion, elect to retain a Construction Manager relative to the Project to oversee the Contractor’s performance of its obligations under the Agreement and the other Project Documents.  If there is no Construction Manager for the Project, all references to the Construction Manager herein should be deemed to be references to the Architect.

    - Construction Manager is District’s Representative.  The Construction Manager shall be the District’s representative during construction of the Work.

    - Communication to be Conducted Through Construction Manager.  If a Construction Manager has been designated by the District for this Project (or upon subsequent written notice from the District or the Architect that a Construction Manager has been appointed, which notice shall identify the Construction Manager), then (a) all communications between the Contractor, on the one hand, and the District and/or the Architect, on the other hand, shall be made through the Construction Manager, and (b) wherever the Project Documents call for the Contractor to deliver any notice or document to the District and/or the Architect, that notice or document shall instead by delivered to the Construction Manager, who shall then forward it to the District and/or the Architect.

    - Authority of Construction Manager.  The Construction Manager has the authority to enforce compliance with the Project Documents and to act on behalf of the District relative to the Project, but only to the extent expressly provided for in the Project Documents.  Without limiting the generality of the foregoing, the Construction Manager shall have the authority: (a) to stop the Work whenever such stoppage may be necessary in the Construction Manager’s reasonable opinion to ensure the proper execution of the Project Documents; (b) to enforce the Contractor’s faithful performance of its obligations under the Agreement and the other Project Documents; and (c) to exercise any and all other authority and responsibility established by law.

    - Contract Administration.  The Construction Manager shall assist the District and the Architect in administering the Project Documents and enforcing the Contractor’s compliance therewith.  The Contractor shall cooperate (and shall cause its Subcontractors to cooperate) with the Construction Manager in this regard.

    - Construction Manager to Monitor Progress of Work.  Among its other duties, the Construction Manager may be required by the District to monitor the progress of the Work.  The Contractor shall cooperate (and shall cause its Subcontractors to cooperate) with the Construction Manager with respect to such its monitoring.  Such monitoring shall not imply that the Construction Manager or the District are in any way responsible for the safety of the Contractor, Subcontractors or their employees, shall not imply that the Construction Manager or the District will supervise the Contractor’s construction methods or personnel, and shall not relieve the Contractor of any of its obligations under the Project Documents.

    - Construction and Staging Areas.  The Contractor shall cooperate with the Construction Manager to minimize the size of the Project’s construction and staging areas.

    - Pre-Construction, Construction and Progress Meetings.  The Construction Manager will chair all pre-construction, construction and progress meetings, which shall occur no less frequently than weekly and which must be attended by the Contractor.  The Construction Manager shall prepare and distribute minutes of those meetings.

- INTERPRETATION AND RELATIONSHIP OF DOCUMENTS

  - Intent of the Project Documents.  The intent of the District in preparing the Project Documents is that the Project Documents be interpreted to include all items necessary for the proper execution and completion of the Work by the Contractor.  Plans and Specifications are intended to delineate and describe the Project and its component parts to such a degree as will enable skilled and competent contractors to intelligently bid upon the Work, and to carry the Work to a successful conclusion.  The Project Documents are complementary, and what is required by any one document shall be binding and required to be performed as part of the Work as if required by all of the Project Documents.  (By way of example and not as a limitation, anything which may be called for in the Specifications and not shown on the Plans or other drawings, or vice versa, shall have the same effect as if called for and/or shown in both.)  The Contractor is required to perform all activities, at no extra cost to the District, which are reasonably inferable from the Project Documents as being necessary to produce the intended results.

  - Purpose of Plans vs. Purpose of Specifications.  Generally, the Specifications address quality, types of materials and contract conditions, while the Plans and other drawings show placement, sizes, fabrication, and details of materials.  The Plans and Specifications are intended to be complementary.

  - Organization of the Plans and Specifications.  The organization of the Specifications into divisions, sections, subsections and paragraphs, and the arrangement of the Plans and other drawings in to disciplines, shall not control the Contractor in dividing the Work among its own forces and/or those of its Subcontractors, and no claim will be entertained by the District based on said organization and arrangement.  The extent of the Work to be furnished by any vender or supplier, or to be performed by any trade or Subcontractor, shall be determined by the Contractor.

  - Questions Regarding Perceived Inconsistencies.  If the Contractor discovers or otherwise becomes aware of any inconsistencies and/or conflicts in the Project Documents, the Contractor shall immediately request an interpretation in writing from the Architect (through the Construction Manger) pursuant to Article 15 below before proceeding with the Work.  If the Contractor fails to make such request and commences or proceeds with the Work or any part thereof without first seeking clarification from the Architect, the (a) the Contractor shall replace or adjust any Work not in conformance (as determined by the Architect) with the Project Documents and shall be responsible for any resultant or added cost, (b) the Contractor waives any claim for extra work or damages as a result of any ambiguity, conflict or lack of information, and (c) no excuse will thereafter be entertained for failure to carry out the Work in a timely or satisfactory manner.

  - Effect of Inconsistencies as to Quality or Quantity.  If the Contractor, the District, the Architect and/or the Construction Manager determine that there is an inconsistency and/or conflict in the quality or quantity of Work required by the Project Documents, the Contractor shall be required to provide – at no extra cost to the District – the greater quality or quantity of Work indicated in accordance with the Architect’s interpretation.

  - Order of Priority Among Conflicting Project Documents.  If the provisions of any of the Project Documents conflict or are inconsistent with the provisions of any other Project Document, the inconsistency or conflict shall be resolved by giving precedence to the Contract Documents in the following order:

    - Addenda, amendments or modifications executed after the execution of the Agreement, the most recent of which shall have priority over those executed earlier;

    - The Agreement, including all exhibits, attachments, appendices, supplements and Addenda referenced therein, with later Addenda having priority over earlier Addenda;

    - These General Conditions;

    - “Division Zero” and “Division One” of the Specifications (as those divisions are identified in the project manual prepared by the District and delivered to the Contractor)

    - The Plans and Specifications (and in the case of an inconsistency between the Plans and Specifications, (a) the better quality or greater quantity of Work shall be provided in accordance with the Architect’s interpretation and (b) the Specifications shall govern as to material, workmanship and installation procedures);

    - The Bid Form; and

    - The Information for Bidders.

  - Conflicts Within the Plans.  If the Plans are internally inconsistent, those inconsistencies shall be resolved as follows:

    - Schedules, when identified as such, shall govern over all other portions of the Plans;

    - Specific notes shall govern over all other notes and all other portions of the plans except the schedules identified in 4.7.1 above;

    - Larger scale drawings shall govern over smaller scale drawings as to shape and details of construction;

    - Figured or numerical dimensions shall govern over dimensions obtained by scaling; and

    - Work not particularly shown or specified shall be the same as similar parts that are shown or specified.

  - Conflicts Within the Specifications.  As to conflicts within the Specifications, these General Conditions shall govern over all other sections of the Specifications, except for specific modifications thereto that may be stated in any Addenda to the Agreement or in any special or supplemental conditions to the Agreement.  No other item in any of the Specifications or other Project Documents shall modify these General Conditions.

  - Conflicts Between Project Documents and Other Documents or Applicable Laws.  If the requirements of any Applicable Laws (as defined in Section 6.1 below), Project Documents, manufacturers’ specifications or industry standards are in conflict, the more restrictive requirements or higher quality mandated by the foregoing shall govern.  In all instances, material and equipment shall be installed in strict accordance with each manufacturer’s most recent published recommendations and specifications.  Furthermore, the Plans and Specifications are intended to comply with all Applicable Laws, and where any of Applicable Law is referred to in the Project Documents, that Applicable Law shall be considered as a part of the Agreement within the limits specified, and the Contractor shall bear all expenses of correcting Work done contrary to said laws, ordinances, rules and regulations if the Contractor (a) performed such Work without first consulting the Architect for instructions or clarification regarding the Work or (b) disregarded the Architect’s instructions regarding that Work.

  - Omissions.  If the Project Documents are not complete as to any minor detail of a required construction system or with regard to the manner of combining or installing of parts, materials, or equipment, but if there exists an accepted trade standard for good and skillful construction, such detail shall be deemed to be an implied requirement of the Project Documents in accordance with such standard.  For all materials and equipment specified or indicated in the Plans and Specifications, the Contractor shall provide all labor, materials, equipment, and services necessary for complete assemblies and complete working systems.  Incidental items not indicated on the Plans and not mentioned in the Specifications, that can legitimately and reasonably be inferred as belonging to the Work, or be necessary in good practice to provide a complete assembly or system, shall be furnished as though itemized in the Plans and Specifications in every detail.  Similarly, if details of work which are manifestly necessary to carry out the intent of the Plans and Specifications, or which are customarily performed, are misdescribed in or omitted from the Plans and Specifications, such details shall be deemed to be an implied requirement of the Project Documents.  In any such case, the omissions or misdescriptions shall not relieve the Contractor from performing such omitted Work, and the Contractor shall perform the same as if fully and correctly set forth and described in the Plans and Specifications.  As used herein, “minor detail” includes without limitation (a) substantially identical components where the price of each such component is small even though the aggregate cost or importance is substantial, and (b) a single component which is incidental, even though its cost or importance may be substantial.  The quality and quantity of the parts or material so supplied shall conform to trade standards and be compatible with the type, composition, strength, size and profile of the parts and materials otherwise set forth in the Project Documents.

  - References to Trade Names.  Materials or other Work described in words which have a well known technical or trade meaning shall be deemed to refer to such recognized standards.  The Project Documents are not intended to include detailed descriptions of any materials or methods commonly known to the trade under any “trade name” or “trade term”.  Instead, the mere mention or notation of such “trade name” or “trade term” shall be considered a sufficient notice to the Contractor that it will be required to complete the Work so named with all of its incidental and accessory items according to the best practices of the trade.

  - Named Materials and Equipment Must Be Furnished and Installed.  The naming of any material and/or equipment shall imply that the Contractor is to furnish and install the same, including all incidental and accessory items thereto and/or labor necessary to achieve full and complete functioning of the material and/or equipment as per the best practices of the trade(s) involved, unless specifically noted otherwise.

  - Substituted Items.  If the Contractor furnishes material, processes, services or equipment more expensive than that specified, any additional cost of such material, process, service, or equipment so furnished shall be borne by the Contractor.  Any engineering, design fees, or approval agencies’ fees required to make adjustments in material or Work of all trades directly or indirectly affected by the approved substituted items shall be borne entirely by the Contractor.  Any difference in cost between an approved substitution which is lower in cost than the originally specified item shall be refunded by the Contractor to the District.  All requests for substitutions shall be done in compliance with the requirements of Section 1630 – Product Substitution Procedures.

  - Detail Drawings and Instructions.  In case of ambiguity, conflict or lack of information which is not resolvable in accordance with the foregoing Sections, the Architect may, at the District’s request, furnish additional instructions by means of drawing or otherwise, as necessary for proper execution of the Work.  All such drawings and instructions shall be consistent with the existing Project Documents, and shall upon completion become part of the Project Documents.  Such additional drawings and instructions shall be furnished with reasonable promptness, provided that the Contractor informs the Architect of the relationship of the request to the critical path of construction.  Work shall be executed in conformity therewith.

  - Ownership of Drawings.  All Plans, Specifications, drawings, designs, and other incidental architectural and engineering work or materials and other Project Documents and copies thereof furnished by the District are District’s property.  They are not to be used in other work and are to be returned to the District on request at completion of the Work, and may be used by the District as it may require, without any additional costs to the District.

  - Other Contracts.  The District reserves the right to let other contracts in connection with the Work or the Project.  Nothing herein contained shall be interpreted as granting to the Contractor exclusive occupancy at the site of the Project.

    - Cooperation Among Contractors.  The Contractor shall afford other contractors reasonable opportunity for introduction and storage of their materials and execution of their work, and the Contractor shall properly connect and coordinate its Work with that of such other contractors.  The Contractor shall not cause any unnecessary hindrance or delay to any other contractor working on the Project.  If simultaneous execution of any Work by the Contractor and any other contractor is likely (in the opinion of the District, the Inspector, the Architect or the Construction Manager) to cause interference with performance of the Work or the contractual obligations of either contractor, then the District shall decide which contractor shall cease work temporarily and which contractor shall continue or whether the Work can be coordinated so that both contractors may proceed simultaneously.

    - Scope of Project.  The Contractor shall ascertain to its own satisfaction the scope of the Project and the nature of any other contracts that have been or may be awarded by the District in connection with the Project, as necessary to allow the Contractor to perform its obligations under the Agreement in the light of such other contracts, if any.

    - No District Liability Relative to Other Contracts.  The District shall not be responsible for any damages suffered or extra costs incurred by the Contractor resulting directly or indirectly from the award, performance or attempted performance of any other contract or contracts relative to the Project, or caused by any decision or omission of the District, the Architect or the Construction Manager regarding the order of precedence in performance of contracts.

- CONSTRUCTION SCHEDULE

  - Commencement, Performance and Completion of Work.  It is expressly understood and agreed that the date on which the Work is commenced, the rate of progress of the Work, and the date on which the Work is completed, are all of the essence of the Agreement and the other Project Documents.  The Work shall be prosecuted at such time, in such manner, and on such part or parts of the Project as may be required to complete the Project as contemplated in Project Documents and the Construction Schedule to be prepared by the Contractor and approved by the District pursuant to the provisions of this Article 5.

  - Preparation of Initial Construction Schedule Upon District’s Notice to Proceed.  The Contractor shall prepare and submit to the District, the Architect and the Construction Manager, an initial Construction Schedule within three (3) business days after the issuance of by the District of a Notice to Proceed with the Work.  The initial Construction Schedule shall be developed using Microsoft Project in the form of a Critical Path Method (CPM) network diagram and shall be sufficient detail to show the sequence of activities required to complete performance of all Work, the early start and early finish dates of activities, and the critical path of the Project.  A tabular report shall accompany the network diagram and shall, at a minimum, include: the activity number for each activity; the description and duration of each activity; all predecessors to and successors from each activity; and the early start, early finish, late start, late finish, and total float for each activity.  The report shall support the network diagram submitted.

  - Work Activities Reflected in Construction Schedule.  The Work Activities comprising the initial Construction Schedule shall be described in sufficient detail to assure the adequate planning has been done for proper execution of the Work and such that the Construction Schedule provides an appropriate basis for monitoring and evaluating the progress of the Work.  Exclusive of those Work Activities for substantial review and material fabrication and delivery, Work Activity duration shall not be less than one (1) nor more than five (5) calendar days, unless otherwise approved by the District.  Work Activities consisting of the Architect’s review of a submittal by the Contractor shall be limited to 30 days unless longer period of time specified elsewhere in the Project Documents.

  - Float.  The initial Construction Schedule shall begin with date of issuance of the Notice to Proceed and conclude with the date on which the Work shall be completed.  The Contractor may submit an initial Contractor’s Construction Schedule which shows that the Work will be competed on an earlier date (the “Early Completion Date”) than the Contractual Completion Date.  However, the acceptance of a Construction Schedule containing an Early Completion Date will not change the Contractual Completion Date.  The Contractual Completion Date shall control in any determination of liquidated damages or extension of time.  The difference in time between the Early Completion Date and the Contractual Completion Date shall be considered as float, slack time or contingency.  Float, slack time, or contingency within the schedule, and total float within the overall schedule, is not for the exclusive use of either the District or the Contractor, but jointly owned by both parties and is a resource available to and shared by both parties as needed to meet Contract milestones and the Contractual Completion Date.  The Contractor shall not sequester shared float time through such strategies as extending activity duration estimates to consume available float, using preferential logic, using extensive crew/resource sequencing, etc.  Since float time within the Construction Schedule is jointly owned, no time extensions will be granted nor delay damages paid until a delay occurs which extends the Work beyond the Contractual Completion Date.  Since float time within the Construction Schedule is jointly owned, it is acknowledged that District-caused delays on the Project may be offset by the District-caused time savings (i.e., critical path submittals returned in less time than allowed by the Agreement, approvals of substitution requests which result in a savings of time to the Contractor, etc.).  In such an event, the Contractor shall not be entitled to receive a time extension or delay damages until all the District-caused time savings are exceeded and the Contractual Completion Date is also exceeded.

  - District’s Approval of Initial Construction Schedule.  The District, within ten (10) business days after receipt of the initial Construction Schedule, shall meet with the Contractor and selected Subcontractors requested by the District, to review the initial Construction Schedule.  Within ten (10) business days thereafter the District shall deliver written comments to the Contractor as to that initial Construction Schedule.  Within ten (10) business days after the District’s delivery of those written comments, the Contractor shall revise the initial Construction Schedule in accordance with District’s comments, and deliver the revised Construction Schedule to the District.  Within twenty (20) days thereafter the District shall either accept the revised Construction Schedule by written notice to the Contractor or deliver to the Contractor additional written comments as to the Construction Schedule.  It is anticipated that not more than two (2) submittals of the initial Construction Schedule will be needed in order to obtain an accepted schedule.  Once accepted by the District, the Construction Schedule shall be relied on by the parties until either an updated schedules is prepared by the Contractor to reflect actual completed Work, approved changes, or recognized delays, and submitted to the District for approval.  When the initial Construction Schedule has been accepted pursuant to this paragraph, the Contractor shall submit to the District three (3) complete copies if the accepted Construction Schedule and network diagram.  That submittal shall be a condition precedent to the processing of the Contractor’s second (2nd) application to the District for payment under the Agreement.

  - Effect of Change Orders.  Upon issuance of a change order or Notice to Proceed for all change orders including time extensions, the approved time extension shall be reflected in the next weekly report submitted by the Contractor pursuant to Section 5.7 below and in the next monthly update submitted by the Contractor pursuant to Section 5.8 below.

  - Weekly Reports.  Once each week, or as approved by the District, the Contractor shall submit a report and schedule listing the activities began, completed, or in progress in the past week, and the activities scheduled to begin, complete or to be in progress for succeeding two (2) weeks.  This report shall cover all work activities listed on the Construction Schedule.  The report or schedule may be submitted in bar chart form or in a schedule narrative document.

  - Monthly Updates.  Five (5) days prior to the submittal of the Contractor’s monthly payment request, the Contractor shall submit an updated Construction Schedule reflecting progress to date, estimated start and completion dates for Work Activities not yet began, status of ongoing activities, approved changes to the Work, and any schedule revisions.  The monthly submittal to the District shall be accompanied by three (3) copies of a bound report.  The bound report shall include the information described in the Contractor’s Schedule Narrative Report Outline listed below:

- CONTRACTOR’S SCHEDULE NARRATIVE REPORT OUTLINE

- Contractor’s transmittal letter

- Description of problem areas (referenced to change order or claim numbers as appropriate)

- Current and anticipated delays not resolved by approved change order, including:

- Cause of the delay

- Correction action and schedule adjustments to correct the delay

- Known or potential impact of the delay or other activities, milestone, and project completion date.

- Changes in construction sequence

- Pending items and status thereof including, but not limited to:

- Pending change orders

- Time extension requests

- Other items

- Project competition date status:

- If ahead of schedule, the number of calendar days ahead

- If behind schedule, the number of calendar days behind

- Other project or scheduling concerns

- Updated network diagram

- Tabular report as specified in (b) above, including a listing of completed activities in progress.

The submittal of the updated Construction Schedule which satisfies the requirements of this Section, accurately reflects the status of the Work and incorporates all changes into the Project, shall be a condition precedent to the processing of the Contractor’s monthly payment application.

  - Additional Revisions Requested by District.  Predicated upon the results of District’s review of monthly submissions of the updated network diagram and schedule narrative, or the joint District/Contractor review in any given month, the Contractor may be required to revise the Construction Schedule.  Conditions under which a revision will be made include the following:

    - When a delay in completion of any Work Activities or sequence of Work Activities results in an indicated extension of the Project completion or interim milestone dates detailed herein by thirty (30) calendar days.

    - When delays in submittals or equipment or material deliveries, or Work stoppages, are encountered which make rescheduling of the Work necessary.

    - When the Construction Schedule does not represent the actual prosecution and progress of the Project.

All revisions and additions to the Construction Schedule are subject to review and acceptance or rejection by the District.

  - Contractor’s Failure to Adhere to Construction Schedule.  If at any time during the Project, the Contractor fails to complete any activity by its latest scheduled completion date, which late completion will impact the end date of the Work past the Contractual Milestone Completion Date(s), then the Contractor shall, within three (3) calendar days, submit to the Construction Manager (a) a written narrative statement as to how and when the Contractor will reorganize the Work to return to the current Construction Schedule and (b) a written recovery schedule showing that such reorganization will not delay or otherwise impact the Work or Work Activity of any other contractor, Subcontractor, or material supplier on the Project.  If any such other contractor, Subcontractor or material supplier asserts a delay claim or other claim against the District as a result of the Contractor’s late completion or reorganization of Work identified in this Section 5.10, then the Contractor shall indemnify, defend and hold the District harmless from and against those claims pursuant to Section 7 of the Agreement.  Whenever it becomes apparent from the current monthly progress evaluation and updated Construction Schedule data that any milestone date(s) (including without limitation the Contractual Completion Date) will not be met, the Contractor shall take some or all of the following actions:

    - Increase construction manpower in such quantities and crafted as shall substantially eliminate the backlog of Work and meet the current Contractual Completion Date.

    - Increase the number of working hours per shift, the number of shifts per day, the number of work days per week, or the amount of construction equipment, or any combination of foregoing sufficient to substantially eliminate the backlog of Work.

    - Rescheduled Work items to achieve concurrent accomplishment of Work Activities.

Under no circumstances will the addition of equipment or construction forces, increasing the working hours, or any other method, manner, or procedure to allow the Project to be completed by the Contractual Completion Date as required hereunder be considered justification for a change order or treated as acceleration.

  - Limitation on Time Extensions and Delay Damages.  It is agreed that no time extensions shall be granted nor delay damages paid unless the delay can be clearly demonstrated by the Contractor on the basis of the updated Construction Schedule current as of the month the change was issued or the delay occurred and which delay cannot be mitigated, offset, or eliminated through actions as revising the intended sequence of work or other means.  MOREOVER, IF THE CONTRACTOR SUBMITS A REVISED CONSTRUCTION SCHEDULE SHOWING AN EARLIER COMPLETION DATE FOR THE PROJECT, THE DISTRICT’S ACCEPTANCE OF THIS REVISED CONSTRUCTION SCHEDULE SHALL NOT ENTITLE THE CONTRACTOR TO ANY DELAY CLAIM OR DAMAGES DUE TO ANY SUCH REVISED CONSTRUCTION SCHEDULE.

- CONTRACTOR’S OBLIGATIONS PRIOR TO COMMENCEMENT OF WORK

  - Knowledge of and Compliance with Applicable Laws.  The Contractor shall familiarize itself with all Applicable Laws.  At all times during the term of the Agreement, the Contractor shall conduct the Work, and shall cause its Subcontractor’s to conduct the Work, in compliance with all Applicable Laws.  The Contractor shall keep on the job site at all times and a copy of Titles 8, 17, 19 and 24 of the California Code of Regulations, and shall be acquainted with and comply with the provisions of said Titles, including without limitation those duties (i) applicable to the Contractor which are codified at Section 4-343 of said Title 24 and (ii) applicable to conditions on the Project site set forth in said Titles 8 and 17.  As used herein, the term “Applicable Laws” shall mean all statutes, ordinances, governmental regulations, judicial orders and other legal requirements applicable to the conduct, performance and/or results of the Work.  Without limiting the generality of the foregoing, Applicable Laws shall include the following, as they existed on the date that the Plans were approved by the DSA (with respect to construction of the Work in accordance with the Plans and Specifications) or as they may hereafter be amended, supplemented, revised or replaced (with respect to all other aspects of the Contractor’s performance under the Agreement):

    - The California Building Code and Amendments.

    - The Construction Safety Rules of the Division of Industrial Safety of the State of California.

    - The National Electric Code.

    - The Uniform Plumbing Code of the Western Plumbing Officials Association.

    - The State Building Code, Title 24, Part 2, California Code of Regulations, including pertinent provisions contained in the Annual Supplements.

    - Title 19, Public Safety, California Code of Regulations.

    - Title 24, Part 1, Building Standards Administrative Code, California Code of Regulations.

    - Federal Standards of Department of Labor, Occupational Safety and Health Administration, and all applicable codes, ordinances and regulations of State, County and City agencies and entities having jurisdiction there over.

    - Specification Standards of Public Works.

  - Examination of Project Documents.  Before commencing any Work, The Contractor shall carefully study and compare all Plans, Specifications and other Project Documents.  If at any time (during the Contractor’s initial review or later) the Contractor observes that the Plans, Specifications, or any other Project Documents appear to conflict with or to be at variance with any Applicable Laws, or appear to contain any error, inconsistency or omission, the Contractor shall promptly notify the Construction Manager in writing, and the Construction Manager shall forward the notice to the District and the Architect.  Any changes to the Project Documents in question deemed necessary by the Architect shall be adjusted as provided for in Section 4.14 above or Article 16 below.  The Contractor shall be liable to the District for damage resulting from errors, inconsistencies, or omissions in the Project Documents that the Contractor recognized and knowingly failed to report, if a similarly skilled, knowledgeable, and experienced contractor would have discovered and reported.

  - Site Investigation.  The Contractor represents and warrants to the District that prior to the execution of the Agreement the Contractor examined the Project site as required by Section 12 of the Information for Bidders.

  - Contractor Shall Inspect for Defects in Existing Work.  If any part of the Contractor’s Work depends for proper execution or results upon the Work of any other contractor or upon any other existing conditions or improvements, the Contractor shall (prior to commencing its own Work) measure and inspect all Work, conditions or improvements already in place and promptly report to the Architect and the Construction Manager in writing (a) any discrepancy between existing Work, conditions or improvements and the requirements set forth in the Project Documents, and (b) any defects in or other aspects of such existing Work, conditions or improvements that will prevent, interfere with or make more difficult the Contractor’s performance of its Work.  The Contractor will be held accountable for any and all damages incurred by the District arising from the Contractor’s failure to measure and inspect Work, conditions and improvements as required by this Section 6.4.  The Contractor’s failure to make the measurements, inspections and reports required by this paragraph shall constitute the Contractor’s acceptance of all such existing Work, conditions and improvements as being suitable and proper to receive the Contractor’s own Work, except as to defects which may develop in other contractors’ work after the Contractor’s performance of its own Work.

  - Soils Investigations and Reports.  Article 6.5. Soils Investigations and Reports. If and when a soils investigation report has been obtained from test holes at the Site, such report will be made available for the Contractor’s use in preparing its bid and Work under this Agreement.  Any information obtained from such report or any other information given on drawings as to subsurface soil condition or to elevations of existing grades or elevations of underlying rock is approximate only. As a result of Contractor’s investigation, any soils conditions encountered by Contractor during the course of Work under this Agreement which are found from zero (0) to four (4) feet below the surface shall be the sole responsibility of the Contractor and Contractor shall be liable for any unforeseen soil conditions. If, during the course of Work under this Agreement, Contractor encounters unforeseen subsurface conditions below the four (4) feet threshold which differ materially from those indicated in the soils investigation report, then Contractor shall notify the District within five (5) calendar days of discovery of the condition, and changes to the contract price may be made in accordance with Article 16 entitled “Changes in the Work.”  Contractor agrees that no claim against District will be made by Contractor for damages and hereby waives any rights to damages in the event the Contractor fails to notify District within the five-day period mentioned above.

- WARNING:  On soil from 0 to 4 feet, DISTRICT DOES NOT WARRANT THE SOILS AT THE PROJECT SITE.  SOILS INVESTIGATION REPORT IS PROVIDED FOR CONTRACTORS INFORMATION ONLY.  CONTRACTOR HAS CONDUCTED AN INDEPENDENT INVESTIGATION OF THE PROJECT SITE AND THE SOILS CONDITIONS OF THE SITE.  DISTRICT DOES NOT WARRANT THE SOILS CONDITIONS OF THE SITE AND CONTRACTOR IS FULLY RESPONSIBLE TO ASCERTAIN SITE CONDITIONS FOR THE PURPOSES OF DETERMINING CONSTRUCTION MEANS AND METHODS PRIOR TO COMMENCING CONSTRUCTION.  THE SOILS INVESTIGATION REPORT IS NOT A CONTRACT DOCUMENT.

The Contractor agrees that no claim against the District will be made by the Contractor for damages in connection with the foregoing, and hereby waives any rights to damages arising out of such subsurface or latent conditions.

  - Layout and Field Engineering.  All field engineering required for laying out of the Work and establishing grades for earthwork operations shall be furnished by the Contractor at its expense.  Such work shall be done by a qualified civil engineer approved by the Architect.

  - Field Measurements and Verification of Dimensions.  The Contractor shall verify all indicated dimensions before ordering materials or equipment, or before performing Work.  The Contractor shall take field measurements, verify field conditions, and shall carefully compare such field measurements and conditions and other information known to the Contractor with the Project Documents before commencing Work.  Errors, inconsistencies or omissions discovered shall be reported to the Construction Manager at once pursuant to Sections 6.2 and 6.4 above.  Upon commencement of any item of Work, the Contractor shall be responsible for dimensions related to such item of Work and shall make any corrections necessary to make the Work properly fit at no additional cost to the District.  This responsibility for verification of dimensions is a non-delegable duty and may not be delegated to Subcontractors or agents.

  - Surveys.  Surveys to determine location of property lines and corners will be supplied by the District.  Surveys to determine locations of construction, grading, and site work shall be provided by the Contractor.

  - Appointment of Contractor’s Superintendent.  Prior to the commencement of the Work, the Contractor shall appoint a competent superintendent (“Contractor’s Superintendent”) satisfactory to the District.  Before commencing the Work, the Contractor shall give written notice to the Construction Manager of the name, qualifications and experience of the Contractor’s Superintendent.  The Contractor’s Superintendent shall be present at the Project site at all times when Work is being conducted.  If the District finds the Contractor’s Superintendent to be unsatisfactory, the Contractor shall replace the Contractor’s Superintendent with one acceptable to the District.  The Contractor’s Superintendent shall not be changed except with the written consent of the District, unless the Contractor’s Superintendent ceases to be employed by the Contractor, in which case the Contractor shall notify the Construction Manager in writing and replace the Contractor’s Superintendent with another person acceptable to the District.  The Contractor’s Superintendent shall represent the Contractor, and all directions given to the Contractor’s Superintendent shall be as binding as if given to the Contractor.  If the Contractor’s Superintendent is not cooperating or is non-responsive to the District, the Architect or the Construction Manager, then the Contractor shall remove the Contractor’s Superintendent and replace him or her with another person acceptable to the District within twenty-four (24) hours after written instructions from the District (delivered by the Construction Manager) to do so.

  - Permits, Licenses, Approvals and Certificates.  The Contractor shall obtain and pay for all permits, licenses, approvals and certificates necessary for the performance of the Work, unless otherwise specified in the Project Documents.  The cost of all such Utility Connection fees and permits, shall be included in the Contractor’s base bid; as such, the amount reimbursable by the District to the Contractor shall be limited to the fee charged by the issuing agency for the Utility Connection fees and permits permit, and shall not include any additional amounts for the Contractor’s profit, overhead or other expenses.  The Contractor shall also maintain the licenses approval or certificate referred to in Section 3.3.2 above, and shall also maintain (and shall require each of its Subcontractors to maintain) any other contractor’s licenses in effect as required by law.  It is the Contractor’s responsibility to ascertain the necessity of such permits, licenses, approvals and certificates, the costs thereof, and any time which may be needed to obtain such permits, licenses, approvals and certificates (which time must be incorporated into the Construction Schedule pursuant to Article 5 above so as not to create delays).

    - Approvals Noted on Plans and Specifications.  Without limiting the generality of the foregoing, if the Plans, Specifications, or other drawings that are part of the Project Documents state that materials, processes, or procedures must be approved by the DSA, the State Fire Marshall, or any other governmental entity or agency, the Contractor shall be responsible for obtaining those approvals.

    - Environmental Clearances.  The Contractor shall provide to state and federal agencies all information necessary for environmental clearances and other authorizations necessary for performance of the Work.  The Contractor shall comply with any and all conditions of such clearances and authorizations, including giving notices during construction when so required.  The Contractor shall not be compensated for any delays in obtaining environmental clearances and authorizations; however, an appropriate extension of time will be granted in accordance with the provisions of Article 14 below, if the Contractor demonstrates to the satisfaction of the District that the Contractor has made every reasonable effort to obtain the requisite clearance or authorizations and cannot obtain same in a timely manner.

  - Insurance.  Prior to commencing the Work, the Contractor shall procure the insurance required by Article 18 below.

- MANNER IN WHICH WORK IS TO BE PERFORMED

  - Contractor’s Supervision of Work.  The Contractor shall supervise and direct the Work competently and efficiently, devoting such attention thereto and applying such skills as may be necessary to perform the Work in accordance with the Project Documents.  The Contractor represents and warrants to the District that the Contractor is a skilled, knowledgeable, and experienced contractor who is able to so supervise and direct the Work.

  - Performance of Work in Violation of Applicable Laws.  If the Contractor performs any work which it knew, or through exercise of reasonable care should have known, to be contrary to Applicable Laws, and failed to give notice to the Construction Manager as required by Section 6.2 above, the Contractor shall bear all costs arising there from.

  - Materials and Work.

    - Payment.  Except as otherwise specifically stated in the Agreement, the Contractor shall provide and pay for all materials, supplies, tools, equipment, labor transportation, superintendence, temporary constructions of every nature, and all other services and facilities of every nature whatsoever necessary to execute and complete the Project within specified time.

    - Quality.  Unless otherwise specified, all materials shall be new and the best of their respective kinds and grades as noted or specified, and workmanship shall be of good quality.

    - Quantity and Availability.  Materials shall be furnished in ample quantities and at such times as to insure uninterrupted progress of work and shall be stored properly and protected as required.

    - Placement of Orders for Materials and Equipment.  The Contractor shall, after issuance of the Notice to Proceed by the District, place orders for materials and/or equipment as specified so that delivery of same may be made without delays to the Work.  Within twenty (20) days after the issuance of the Notice to Proceed, the Contractor shall prepare and deliver to the Construction Manager a procurement schedule identifying the dates on which each such order has been or will be placed.  The Contractor shall, upon demand from the Architect or Construction Manager, furnish to the Architect and Construction Manager documentary evidence showing that orders have been placed and that scheduled delivery dates will be met.  If the Contractor fails to do so, the District reserves the right to place orders for such materials and/or equipment as it may deem advisable in order that the Work may be completed by the Contractual Completion Date, and all expenses incidental to the procuring of said materials and/or equipment shall be paid for by the Contractor.

    - Ownership, Title, Storage and Inventory.  No materials, supplies, or equipment for work under the Agreement shall be purchased subject to any chattel mortgage or under a conditional sale or other agreement by which an interest therein or in any part thereof is retained by seller or supplier.  The Contractor warrants good title to all material, supplies, and equipment installed or incorporated in the Work and agrees upon completion of all Work to deliver the Project site, together with all improvements and appurtenances constructed or placed thereon by the Contractor, to the District free from any claims, liens, or charges.  The title to new materials and/or equipment and attendant liability for its protection and safety, shall remain in the Contractor until incorporated in the Work and accepted by the District.  No part of said materials and/or equipment shall be removed from its place of storage except for immediate installation in the Work.  The Contractor shall keep an accurate inventory of all said materials and/or equipment in a manner satisfactory to the District or its authorized representative.

  - Integration of Work.  The Contractor shall do all cutting, fitting, patching, and preparation of Work as required to make its several parts come together properly, and fit it to receive or be received by Work of other contractors or existing conditions shown upon, or reasonably implied by, the Plans and Specifications, and shall follow all directions given by the Construction Manager on behalf of the District or the Architect.

    - Costs Associated with Integration Work.  All costs caused by defective or ill-timed Work shall be borne by the Contractor.

    - Damage to Existing Work.  The Contractor shall not endanger any Work by cutting, excavating, or otherwise altering Work and shall not cut or alter Work of any other contractor without the written consent of the Architect.  The Contractor shall be solely responsible for protecting existing Work on adjacent properties and shall obtain all required permits for shoring and excavations near property lines.

    - Matching Existing Work.  When modifying existing work or installing new Work adjacent to existing work, the Contractor shall match, as closely as conditions of site and materials will allow, the finishes, textures, and colors of the original work, refinishing existing work as required, at no additional cost to the District.

    - Effect on Integration of Phased Project.  The Contractor is aware that the Project may be split into several phases.  If the Project is split into phases then the Contractor has made allowances for any delays or damages which may arise from coordination with contractors for other phases.  If any delays should arise from a contractor working on a different phase, the Contractor’s sole remedy for damages, including delay damages, shall be against the contractor who caused such damage and not the District.  The Contractor shall provide access to contractors for other phases as necessary to prevent delays and damages to contractors working on other phases of construction.

  - Coordination With Other Work.  The District reserves the right to do other work in connection with the Project or adjacent thereto by contract or otherwise, and the Contractor shall at all times conduct its Work so as to impose no hardship on the District or others engaged in the District’s work nor to cause any unreasonably delay or hindrance thereto.  Where two or more contractors are employed on related or adjacent work, each shall conduct their operations in such a manner as not to cause delay or additional expense to the other.

  - Tests and Inspections.  If the Project Documents. the District’s written instructions, or any laws, ordinances or orders of any public authority require any Work to be specially tested or approved, then the Contractor shall give notice of the Work’s readiness for observation or inspection at least two (2) working days prior to being tested or covered.  If inspection is by authority other than the District, the Contractor shall inform the District’s Inspector of the date fixed for such inspection.  Required certificates of inspection shall be secured by the Contractor.  Observations by District’s Inspector shall be promptly made, and where practicable, at source of supply.  If any Work should be covered without approval or consent of District’s Inspector, the Work must be uncovered for examination and satisfactorily reconstructed at the Contractor’s expense in compliance with the Agreement.  Costs of tests, inspections, re-inspections, and any materials found to be not in compliance with the Agreement shall be paid for by the Contractor.  Other costs for test and inspection shall be paid by the District.  Tests and inspections will comply with California Code of Regulations Title 24, Section 4-335.

  - Trenches.  The Contractor shall provide adequate sheeting, shoring, and bracing, or an equivalent method, for the protection of life and limb in trenches and open excavation which conform to all Applicable Laws (as that term is defined in Section 6.1 above).  If the Agreement involves the excavation of any trench or trenches five feet or more in depth, then no excavation of such trench or trenches shall be commenced until the Contractor has delivered to the Construction Manager evidence that the Contractor has obtained the permit or permits required in connection therewith pursuant to Labor Code Section 6500.

  - Removal and Restoration of Existing Utility Lines.

    - Extent of District’s Responsibility.  Pursuant to Government Code Section 4215, the District assumes the responsibility for removal, relocation, and protection of utilities located on the construction site at the time of commencement of construction under the Agreement with respect to any such utility facilities which are not identified in the Plans and Specifications.  Notwithstanding anything to the contrary set forth in this Section 7.8, however, the parties agree  that except for identification in the Project Documents of main or trunk line utility facilities, the provisions of this Section 7.8 shall not apply to, and the District shall have no obligation to indicate, the presence of existing service laterals or appurtenances whenever the presence of such utilities on the Project site can be inferred from the presence of other visible facilities, such as buildings, meter and junction boxes, on or adjacent to the Project site.

    - Discovery of Utility Facilities Not Shown on Plans and Specifications.  If the Contractor, while performing Work under the Agreement, discovers utility facilities not identified by the District in the Plans or Specifications, the Contractor shall immediately notify the Construction Manager and the utility involved.

    - Compensation to Contractor in Connection with Utility Lines.  When the Contractor is required to locate, remove or relocate utility facilities not identified in the Project Documents with reasonable accuracy, the Contractor shall be compensated for the cost thereof.  The Contractor shall also be compensated for the costs of repairing any damage resulting from the discovery of such unidentified utility facility when such damage does not result from the failure of the Contractor to exercise reasonable care.  All such compensation to the Contractor shall be base on an actual cost plus nine percent (9%) mark-up, in lieu of fifteen percent (15%) mark-up as identified in Article 16.

    - District’s Performance of Repair or Relocation Work.  The District (or the public utility, where it is the owner of the utility facilities) shall have the sole discretion to perform repairs, or relocation work at a reasonable price, where such work is required to facilitate the Project.

    - Contractor’s Responsibility.  Except as expressly provided in this Section 7.8, the Contractor shall be responsible at its own cost for all work, expense or special precautions caused by the existence or proximity of utilities encountered at the Project site or in the performance of the Work, including without limitation the repair of any damage resulting from hand or exploratory excavation or any other damage that may result from the existence or proximity of those utilities.  The Contractor is cautioned that the utilities encountered at the Project site may include communications cables or electrical cables conducting high voltage.  When excavating in the vicinity of the ducts enclosing such cables, special precautions are to be observed by the Contractor at its own cost and shall include the following: all cables and their enclosure ducts shall be exposed by careful hand excavation so as not to damage the ducts or cables nor cause injury to persons; and appropriate warning signs, barricades and safety devices shall be erected.  As part of any Work to be performed by the Contractor hereunder, the Contractor shall provide the notices required by, and shall proceed in accordance with, Government Code Sections 4216.2, 4216.3 and 4216.4, and the Contractor pay all fees charged pursuant to Government Code Sections 4216 et seq.

    - Contractor to Provide Drawings of Utilities.  The Contractor shall provide to the Construction Manager (for delivery to the Architect and the District) as-built drawings of all utilities encountered and constructed to the Project site, indicating the size, horizontal location, and vertical location based on the Project bench mark or a stable datum.

    - No Liquidated Damages.  The Contractor shall not be assessed liquidated damages for delay in the completion of the Project which delay is caused by the failure of the District or the owner of the utility to provide for removal or relocation of such unidentified utility facilities.

    - Assessment for Other Delays.  Notwithstanding Section 7.8.7 above, this Section 7.8 shall not be construed to preclude assessment against the Contractor for any other delays in completion of the Work.

  - Minimizing Interference with School Operations.  If the Project site includes all or any portion of a school facility operated by the District, then all construction activities, all loading and unloading of construction materials and equipment, and all other Work, will be scheduled and conducted so as to minimize disruptions to (a) the District’s operation of the school facility, including student testing and tests, (b) campus activities, and (c) campus users.  The Contractor shall also take the precautions set forth in Section 7.10.5 below.

  - Protection of Persons and Property.

    - Protection Against Damage.  The Contractor shall be responsible for all damages to persons or property that occur as a result of its fault or negligence in connection with the prosecution of the Agreement and shall take all necessary measures and be responsible for the proper care and protection of all materials delivered and Work performed until completion and final acceptance by the District.  The Contractor shall provide such heat, covering, and enclosures as are necessary to protect all work, materials, equipment, appliances, and tools against damage by weather conditions.  All Work shall be solely at the Contractor’s risk with the exception of damage to the work caused by “acts of God” as defined in Public Contract Code Section 7105.

    - Safety of Personnel.  The Contractor shall take, and require subcontractors to take, all necessary precautions for safety of workers and shall comply with all applicable federal, state, local and other safety laws, standards, orders, rules, regulations, and building codes to prevent accidents or injury to persons on, about, or adjacent to the Work site and to provide a safe and healthful place of employment.  The Contractor shall furnish, erect and properly maintain at all times, as directed by the District or the Architect or required by conditions and progress of Work, all necessary safety devices, safeguards, construction canopies, signs audible devices for protection of the blind, safety rails, belts and nets, barriers, lights, and watchmen for protection of workers and the public and shall post danger signs warning against hazards created by such features in the course of construction.  The Contractor shall designate a responsible employee, whose duty shall be to post information regarding protection and obligations of workers and other notices required under occupational safety and health laws, to comply with reporting and other occupational safety requirements, and to protect the life, safety and health of workers.  Name and position of person so designated shall be reported in writing to the District by the Contractor.  The Contractor shall correct any violations of safety laws, standards, orders, rules, or regulations.  Upon the issuance of a citation or notice of violation by the Division of Occupational Safety and Health, such violation shall be corrected immediately by the Contractor at the Contractor’s expense.

    - Emergency Action by Contractor.  In an emergency affecting safety of persons, Work or adjoining property, the Contractor, without special instruction or authorization from the Architect, the Construction Manager or the District, is hereby permitted to act at the Contractor’s discretion to prevent such threatened loss or injury.  Furthermore, the Contractor shall take such actions if expressly instructed by the Construction Manager.  Any compensation claimed by the Contractor on account of emergency work shall be determined by written agreement with the District.

    - Protection of Existing Structures and Facilities.  The Contractor shall take adequate precautions to protect existing roads, sidewalks, curbs, pavements, utilities, adjoining property and structures (including, without limitation, protection from settlement or loss of lateral support), and to avoid damage thereto, and repair any damage thereto caused by construction operations.

    - Safety of Students.  When performing new construction on existing school sites, the Contractor shall (a) become informed and take into specific account the maturity of the students on the site, (b) perform work which may interfere with school activities only before or after school hours, (c) enclose Work areas with a substantial barricade, and (d) arrange the Work to cause a minimum amount of inconvenience and danger to students and faculty in their regular school activities.

    - Protection of Shrubs and Trees.  The Contractor shall provide substantial barricades around all shrubs or trees in the vicinity of the Work, except with respect to any shrubs or trees which the Construction Manager specifies by written notice to the Contractor are not required  to be preserved.

    - Material Delivery Routes.  The Contractor shall deliver materials to Work sites over routes designated by the Construction Manager.

    - Dust Abatement.  The Contractor shall take preventive measures to eliminate objectionable dust.

    - Enforcement of District Rules and Regulations.  The Contractor shall, to the extent directed by the Construction Manager, enforce all District policies and procedures regarding signs, advertising, fires, and smoking, and shall require that all workers at the Project site comply with all such rules and regulations while on the Project site.

    - Survey Markers and Monuments.  The Contractor shall take care to prevent disturbing or covering any survey markers, monuments, or other devices marking property boundaries or corners.  If the Contractor or any Subcontractor accidentally disturbs any such marker, monument or device, then the Contractor shall at its expense cause a civil engineer approved by the District to replace the marker, monument or device.

  - Utilities and Facilities at Project Site.  At all times during the Contractor’s and Subcontractors’ performance of the Work, the Contractor shall maintain the following utilities and facilities at the Project site:

    - Utilities.  All utilities necessary for the performance of the Work – including without limitation electricity, water, gas, and telephone – shall be furnished and paid for by the Contractor.  The Contractor shall also furnish and install all related and necessary temporary distribution systems for those utilities (including meters, if necessary) from distribution points to points on the Project site where utility service is necessary to carry on the Work.  Upon completion of the Work, the Contractor shall remove all temporary utility distribution systems.  If the Project consists of the construction of additions to existing facilities, the Contractor may, with written permission of the District, use the District’s existing utilities by making prearranged payments to the District for utilities used by the Contractor for construction.

    - Inspector’s Field Office.  The Contractor shall provide a temporary field office for the Inspector’s exclusive use; with the District’s consent that field office may be a designated area of, or an office contained within, the Contractor’s field office.  The minimum size of the Inspector’s field office shall be as specified in Section 18 of the Agreement.  The field office shall be located as directed by the Inspector and shall be maintained by the Contractor until removal is authorized by the District.  The field office shall be of substantial waterproof construction with adequate natural light and ventilation by means of stock design windows.  If that field office consists of a separate trailer or building, or of a separate room within the Contractor’s field office, then the door(s) to the Inspector’s field office shall have a key type lock or padlock hasp; otherwise, the Inspector’s field office shall contain lockable file cabinets of a type and in such amount as designated by the Inspector.  The Contractor shall at no additional charge equip the field office with a table satisfactory for study of plans and with two chairs.  The Contractor shall provide and pay for adequate electric lights, telephone service (not a pay phone) consisting of at least one separate voice line, one separate fax line and one separate data line, access to the Contractor’s on-site photocopy machine(s); and adequate heat, ventilation and air conditioning for the field office until authorized removal.

    - Sanitary Facilities.  The Contractor shall provide sanitary temporary toilet facilities in no fewer numbers than required by law and such additional facilities as may be directed by the Inspector for the use of all persons working at the Project site.  The toilet facilities shall be maintained in a sanitary condition at all times and shall be left at the site until removal is directed by the Inspector.  Use of the permanent toilet facilities that are part of the Work under construction shall not be permitted.

  - Sound and Noise Controls.  The Contractor shall comply with all sound control and noise level rules, regulations and ordinances which apply to the Work.  In the absence of any such rules, regulations and ordinances, the Contractor shall conduct the Work so as to minimize disruption to others due to sound and noise caused by the Work, and shall be responsive to the District’s or the Construction Manager’s requests to reduce noise levels.  Each internal combustion engine used for any purpose on the Project or related to the Project shall be equipped with a muffler of a type recommended by the manufacturer.  No internal combustion engine shall be operated on the Project without a muffler.

  - Emission Controls.  Construction equipment shall be fitted with modern emission control devices and shall be kept in proper tune.

  - Archeological Artifacts.  If the Contractor discovers any artifacts during excavation and/or construction, the Contractor shall stop all affected work and notify the District, which will call in a qualified archaeologist designated by the California Archaeological Inventory to assess the discovery and suggest any further mitigation that the archeologist deems necessary.  If the Contractor discovers human remains, the Contractor shall notify the District, and the District shall be responsible for contacting the county coroner and a qualified archaeologist.  If the remains are determined to be Native American, the District shall contact the appropriate tribal representatives to oversee removal of the remains.

  - Cleanup of Project and Work Site.  The Contractor at all times shall keep the Project site free from debris such as waste, rubbish, and excess materials and equipment caused by the Work.  The Contractor shall not leave debris under, in, or about the Work site, but shall promptly remove same.  Upon completion of the Work, the Contractor shall clean the interior and exterior of all buildings that are part of the Project or otherwise involved in the Work, including fixtures, equipment, walls, floors, ceilings, roofs, window sills and ledges, horizontal projections, and any areas where debris has collected.  The Contractor shall clean and polish all glass, plumbing fixtures, and finish hardware and similar finish surfaces and equipment and shall remove temporary fencing, barricades, planking, sanitary facilities and similar temporary facilities from the Project site.  If the Contractor fails to clean up as required by this Section, the District shall do so and the cost thereof shall be charged to the Contractor.

  - Payments by Contractor.  The Contractor shall pay for the following goods and services at the following times:

    - Transportation and Utilities.  The Contractor shall pay for all transportation and utility services not later than the twentieth (20th) day of the calendar month following that in which such services are rendered.

    - Materials, Tools and Equipment.  The Contractor shall pay for all materials, tools, and other expendable equipment to the extent of ninety percent (90%) of cost thereof, not later than the twentieth (20th) day of the calendar month following that in which such materials, tools, and equipment are delivered at site of Project, and shall pay the balance of the cost thereof not later than the thirtieth (30th) day following completion of that part of the Work in or on which such materials, tools, and equipment are incorporated or used.

    - Amounts Owed to Subcontractors.  The Contractor shall pay to each of its Subcontractors, not later than the tenth (10th) day following each payment by the District to the Contractor the respective amounts allowed the Contractor on account of work performed by the respective Subcontractor to the extent of such Subcontractor’s interest therein.

  - Liens and Lien Releases.  The Contractor agrees that neither it nor any person, firm, or corporation furnishing any materials or labor for any Work covered by the Agreement shall have any right to lien upon premises or any improvement or appurtenance thereon, except that the Contractor may install metering devices or other equipment of utility companies or of political subdivisions, title to which is commonly retained by utility company or political subdivision.  In the event of installation of any such metering device or equipment, the Contractor shall advise the District as to owner thereof.  Nothing contained in this Section 7.17, however, shall defeat or impair the rights of persons furnishing material or labor under any bond given by the Contractor for their protection or any rights under any law permitting such persons to look to funds due the Contractor in hand of the District, and this provision shall be inserted in all subcontracts and material contracts and notice of its provisions shall be given to all persons furnishing materials or labor when no formal contract is entered into for such materials or labor.  The Contractor agrees that at any time upon the request of the District, the Architect or the Construction Manager, the Contractor will submit a sworn statement setting forth the work performed or material furnished by subcontractors and material men, and the amount due and to become due to each, and that before the final payment called for under the Contract the Contractor will, if requested, submit to the District (with copies to the Architect and the Construction Manger) a complete set of vouchers showing what payments have been made for materials and labor used in connection with the Work.  The Contractor and all Subcontractors and material suppliers under the Contractor’s control shall as a condition of receipt and processing of pay requests by the District, submit conditional and unconditional lien releases as applicable.  Failure by the Contractor and its Subcontractors and material suppliers to comply with this requirement will result in the rejection of the pay requests, and payment thereon will be suspended pending compliance with this requirement.  Upon compliance, the District will re-commence processing of such pay requests.

  - District’s Access to Work.  The District and its representatives shall at all times have access to the Work wherever it is in preparation or progress.  The Contractor shall provide safe and proper facilities for such access so that the District’s representatives may perform their functions.

7.19	District’s Right to Perform Work.  If the Contractor defaults or neglects to carry out the Work in accordance with the Contract Documents, including, but not limited to:

1.	Failure to supply adequate workers on the entire Project or any part thereof;

2.	Failure to supply a sufficient quantity of materials;

3.	Failure to perform any provision of this Contract;

4.	Failure to comply with safety requirements, or due to Contractor is creation of an unsafe condition;

5.	In the case of bona fide emergency;

6.	Failure to order materials in a timely manner;

7.	Failure to prepare deferred-approval items or shop drawings in a timely manner;

8.	Failure to comply with Contractor’s schedule which would result in a delay to the critical path;

9.	Failure to comply with the Subletting and Subcontracting Fair Practices, Public Contract Code section 4100, et seq.

If the Contractor defaults or neglects to carry out the Work in accordance with the Contract Documents, and fails (within a seven (7) day period after receipt of written notice or a shorter time period expressly stated in the written notice from the District in an emergency situation) to commence and continue correction of such default with diligence and promptness, the District may correct such deficiencies without prejudice to other remedies the District may have, including those set forth in Article 14 after providing five-day written notice to Contractor and Surety.  If during this seven (7) day period, Surety personally delivers notice to District that it intends to perform such work, District shall allow Surety seven (7) days to perform. In an emergency situation, the District may correct such deficiencies without prejudice to other remedies the District may have, including those set forth in Article 14 after providing 48 hours notice to the Contractor. In either case, the Contractor will be invoiced the cost of correcting such deficiencies, including compensation for additional services and expenses made necessary by such default, or neglect.  The invoice amount shall be deducted from the next payment due the Contractor.  If payments then or thereafter due the Contractor are not sufficient to cover such amounts, the Contractor shall pay the difference to the District.

- COMPLETION OF WORK

  - Finished Work.  The Contractor shall be responsible to see that the finished work complies accurately with the Project Documents.

  - Walk-Through As Prerequisite to Determination of Completion.  When the Contractor believes that the Work is complete except for minor corrective items, it shall so notify the Construction Manager.  Promptly thereafter, the Construction Manager shall schedule a final walk-through of the Project by the Contractor, the District, the Architect, the Inspector and the Construction Manager to determine whether and to what extent the Work is complete.  Any erroneous claims of completion by the Contractor resulting in a premature walk-through shall be at the Contractor’s sole cost and expense, and the District shall be entitled to reduce its payments to the Contractor under the Agreement by an amount equal to any costs incurred by the District due to the erroneous claims by the Contractor that the Project is complete.  Minor corrective (or “punch-list”) items shall be identified in the final walk-through of the Project.

  - District’s Acceptance of Work.  The District, in its sole discretion, may either (a) accept the Work as complete notwithstanding the need to complete minor corrective items (as distinguished from incomplete items), if the Work has otherwise been completed to the satisfaction of the District and the Inspector, or (b) refrain from accepting the Work as complete until the entire Work and all portions thereof, including all punch-list items, have been completed to the satisfaction of the District and the Inspector.  The Work shall only be accepted as complete by an action of the District’s School Board.

  - Notice of Completion.  Once the District has accepted the Work pursuant to Section 8.3 above, the District shall thereafter cause a Notice of Completion to be recorded in the Orange County Recorder’s Office.

  - Contractor’s Failure to Correct Punch-List Items.  If the Contractor fails to complete the minor corrective items prior to the expiration of the thirty-five (35) day period immediately following recording of the Notice of Completion, the District shall withhold from the final payment owing to the Contractor under the Agreement an amount equal to twice the estimated cost, as determined by the District, of each item until such time as the item is completed.  At the end of such 35-day period, if there are items remaining to be corrected, the District may elect to proceed as provided in Section 21.9.

  - Rejection and Correction of Work.  If at any time, before or after completion of the Work, the District discovers that the Contractor has varied from the Plans, Specifications or other drawings, or otherwise failed to perform the Work in accordance with the Project Documents, then the District shall, after consultation with the Architect, either (a) reject any and all such Work, or (b) deduct from any amounts due to the Contractor the sum of money equivalent to the difference in value between the Work performed and that called for by the Plans, Specifications and drawings.  If the district rejects such Work then the Contractor shall promptly remove all Work and materials identified by the District as failing to conform to the Project Documents, whether incorporated or not.  The Contractor shall promptly replace and re-perform its own Work to comply with Project Documents without additional expense to the District and shall bear the expense of making good all Work of other contractors destroyed or damaged by such removal or replacement.  If the Contractor does not remove such Work within a reasonable time, fixed by written notice, the District may remove it and may store any usable material related thereto at the Contractor’s expense.  If the Contractor does not pay expenses of such removal within seven (7) days, the District may, upon seven (7) days written notice, sell such materials at auction or at private sale and shall account for net proceeds thereof, after deducting all costs and expenses that should have been borne by the Contractor.

- WAGES, HOURS AND WORK FORCE

  - Contractor to Supply Sufficient Workforce.  The Contractor shall be responsible for providing a sufficient work force as necessary to meet scheduled commencement, completion and other milestone dates set forth in the Construction Schedule.  Overtime and/or weekend work necessary to meet Contractual Completion Date or any other date(s) identified in the Construction Schedule shall not constitute a basis for a claim for additional compensation.   The Contractor may determine whether to utilize split shifts or overtime compensation for timely completion.

  - Duty to Provide Fit Workers.  The Contractor and its Subcontractors shall at all times enforce strict discipline and good order among their employees and shall not employ on the Project any unfit person or anyone not skilled in the Work assigned to such person.  It shall be the Contractor’s responsibility to ensure compliance with this Section 9.2.  If the Construction Manager, the Architect or the District, in their sole discretion, deems that any person engaged by the Contractor or any Subcontractor in the Work is incompetent, unfit, troublesome or otherwise undesirable, then the Construction Manager shall so notify the Contractor, and the Contractor shall immediately exclude that person from the Project site and shall not again employee that person upon the Project without the prior written consent of the District and the Construction Manager.  If the Contractor fails to exclude such person from the Project site, the District shall (without limiting any of the District’s other rights) have the right to do so.

  - Prevailing Wages.

    - Availability of Information as to Prevailing Wage Rates.  Prevailing wage rates are available from the District or on the Internet at: <http://www.dir.ca.gov>. The Contractor shall post a copy of such wage rates at appropriate conspicuous points on the site of the Project, including a schedule showing all determined minimum wage rates and all authorized deductions, if any, from unpaid wages actually earned.

    - Contractor Must Pay Prevailing Wages.  The Contractor shall pay and shall cause to be paid each worker engaged in Work on the Project not less than the general prevailing rate of per diem wages determined by the Director of the Department of Industrial Relations, regardless of any contractual relationship which may be alleged to exist between the Contractor or any subcontractor and such workers.

    - Holiday and Overtime Rates.  Work performed on holidays, and overtime Work when permitted by law, shall be paid for at a rate of at least one and one-half times the above specified rate of per diem wages, unless otherwise specified.  Holidays shall be defined in the collective bargaining agreement applicable to each particular craft, classification or type of worker employed.

    - Prevailing Waged Include Health & Welfare, Pension, Vacation, Travel Time and Subsistence Payments.  Pursuant to Labor Code Section 1773.1, per diem wages are deemed to include employer payments for health and welfare, pension, vacation, travel time, and subsistence pay as provided for in Labor Code Section 1773.8.  The Contractor shall pay all such payments as defined in the applicable collective bargaining agreements filed with the Department of Industrial Relations in accordance with Labor Code Section 1773.8.

    - Rates for Unclassified Work.  Any worker employed to perform Work on the Project, which Work is not covered by any craft or classification listed in the general prevailing rate of per diem wages determined by the Director of the Department of Industrial Relations, shall be paid not less than the minimum rate of wages specified therein for the craft or classification which most nearly corresponds to work to be performed by them, and such minimum wage rate shall be retroactive to time of initial employment of such person in such craft or classification.

    - Changes to Prevailing Rate Published After Solicitation of Bids.  The prevailing rates payable by the Contractor hereunder are those obtained by the District at the time bids for the Work were solicited, regardless of any subsequent determination by the Director of the Department of Industrial Relations of a change in any prevailing rate of per diem wages in the locality in which the Work is to be performed.

    - Penalty to Contractor for Failure to Pay Prevailing Rates.  Pursuant to Labor Code Section 1775, the Contractor shall as a penalty to the District forfeit up to Two Hundred Dollars ($200) for each calendar day, or portion thereof, for each worker paid less than the prevailing rate of per diem wages, determined by the Director of the Department of Industrial Relations, for such craft or classification in which such worker is employed for any Work done under the Agreement by the Contractor or by any of its Subcontractors.  The amount of the penalty shall be determined by the California State Labor Commission and shall be based on consideration of the Contractor’s mistake, inadvertence or neglect in failing to pay the correct prevailing rate of per diem wage, or the previous record of the Contractor in meeting his or her prevailing rate of per diem wage obligations, or the Contractor’s willful failure to pay the correct prevailing rate of per diem wages.  A mistake, inadvertence or neglect in failing to pay the correct prevailing rate of per diem wage is not excusable if the Contractor had knowledge of his or her obligations under the Agreement and the Applicable Laws.  The difference between such prevailing rate of per diem wage and the amount paid to each worker for each calendar day or portion thereof for which each worker was paid less than the prevailing rate of per diem wage shall be paid to each worker by the Contractor.

  - Apprentices.  The Contractor acknowledges and agrees that, if the Agreement involves a dollar amount greater than or a number of working days greater than that specified in Labor Code Section 1777.5, then the Agreement is governed by the provisions of Labor Code Section 1777.5 with respect to the use of properly registered apprentices, and all of the following provisions shall apply:

    - Use of Apprentices.  Apprentices of any crafts or trades may be employed and, when required by Labor Code Section 1777.5, shall be employed upon the Project, provided they are properly registered in full compliance with the provisions of the Labor Code.  In employing apprentices, the Contractor and each Subcontractor shall also comply with Labor Code Section 1777.6, which forbids certain discriminatory practices in the employment of apprentices.  It shall be the Contractor’s responsibility to ensure compliance with this Section 9.4 and with laws relative to the use of apprentices, including without limitation Labor Code Sections 1777.5, 1777.6 and 1777.7 and Title 8, Sections 200 et seq., of the California Code of Regulations.  The Contractor shall become fully acquainted with all such laws regarding apprentices prior to commencement of the work.  The District suggests that the Contractor contact the State Division of Apprenticeship Standards with any questions regarding laws applicable to apprentices.

    - Payment to Apprentices.  Every such apprentice shall be paid the standard wage paid to apprentices under the regulations of the craft or trade at which he or she is employed, and shall be employed only at the work of the craft or trade to which he or she is registered.

    - Apprenticeship Standards and Agreements.  Only apprentices, as defined in Labor Code Section 3077, who are in training under apprenticeship standards and written apprentice agreements under Chapter 4 (commencing at Section 3070), Division 3 of the Labor Code, are eligible to be employed on public works (including the Project).  The employment and training of each apprenticeship shall be in accordance with the provisions of the apprenticeship standards and apprentice agreements under which he or she is training.

    - Certificate Approving Contractor or Subcontractor Under Applicable Apprenticeship Standards.  Pursuant to Labor Code Section 1777.5, the Contractor and any Subcontractors employing workers in any apprenticeship craft or trade in performing any work under the Agreement shall apply to the applicable joint apprenticeship committee for a certificate approving the Contractor or Subcontractor under the applicable apprenticeship standards for the employment and training of apprentices.  The Contractor and its Subcontractors shall each submit contract award information to the applicable joint apprenticeship committee which shall include an estimate of journeyman hours to be performed under the Agreement, the number of apprentices to be employed and the approximate dates the apprentices will be employed.

    - Evidence of Compliance.  At any time upon the request of the Construction Manager, the Contractor shall provide the Construction Manager with evidence satisfactory to the District of the Contractor’s compliance with the provisions of this Section 9.4.

    - Contractor’s Failure to Comply with Laws Regarding Apprentices.  If the Contractor or Subcontractor willfully fails to comply with Labor Code Section 1777.5, then, upon a determination of noncompliance by the Administrator of Apprenticeship, the Contractor or Subcontractor shall: (a) be denied the right to bid on any subsequent District project for one year from the date of such determination; and (b) forfeit as a penalty to the District one hundred dollars ($100) per day for each calendar day of noncompliance, which shall be withheld from any payment due or to become due under the terms of the Agreement.  Interpretation and enforcement of these provisions shall be in accordance with the rules and procedures of the California Apprenticeship Council.

  - Hours of Work.

    - Eight-Hour Day.  As provided in Article 3, (commencing at Section 1810), Chapter 1, Part 7, Division 2 of the Labor Code, eight (8) hours of labor shall constitute a legal day’s work.  The time of service of any worker employed at any time by the Contractor or by any Subcontractor on any subcontract under the Agreement upon the work or upon any part of the work contemplated by the Agreement shall be limited and restricted by the Agreement to eight (8) hours per day, and forty (40) hours during any one week, except as hereinafter provided.  Notwithstanding the provisions hereinabove set forth, Work performed by employees of the Contractor or Subcontractor in excess of eight (8) hours per day, or forty (40) hours during any one week, shall be permitted upon this public work upon compensation for all hours worked in excess of eight (8) hours per day at not less than one and one-half times the basic rate of pay.

    - Record of Hours.  The Contractor shall keep and shall cause each Subcontractor to keep an accurate record showing the name of and actual hours worked each calendar day and each calendar week by each worker employed by the Contractor or Subcontractor in connection with the work or any part of the work contemplated by the Agreement.  The record shall be kept open at all reasonable hours to the inspection of the District and to the Division of Labor Standards Enforcement, Department of Industrial Relations.

    - Penalty Payable by Contractor Relative to Overtime.  Pursuant to Labor Code Section 1813, the Contractor shall pay to the District a penalty of Twenty-Five Dollars ($25) for each worker employed in the execution of this Contract by the Contractor or by any Subcontractor for each calendar day during which such worker is required or permitted to work more than eight (8) hours in any one calendar day and forty (40) hours in any one calendar week in violation of the provisions of Article 3 (commencing at Section 1810), Chapter 1, Part 7, Division 2 of the Labor Code.

    - No Additional Expense to District for Overtime.  Any Work necessary to be performed after regular working hours, or on Sundays or other holidays shall be performed without additional expense to the District.

  - Provision of First Aid to Workers.  The Contractor shall maintain emergency first aid treatment for the Contractor’s workers on the Project which complies with the Federal Occupational Safety and Health Act of 1970 (29 U.S.C.A., Sec. 651 et seq.).

- DOCUMENTATION

  - Documentation of Work.  The Contractor shall keep on the job site at all times one legible copy of all Project Documents, including without limitation Addenda, change orders, Plans, Specifications, drawings and schedules.  Said documents shall be kept in good order and available to the District, the Architect, the Inspector(s), the Construction Manager, and all governmental entities having jurisdiction over the Project.

  - District’s Audit Rights.  Pursuant to and in accordance with the provisions of Government Code Section 8546.7, or any amendments thereto, all books, records and files of the District, the Contractor, or any Subcontractor or material supplier connected with the performance of the Agreement involving the expenditure of public funds in excess of Ten Thousand Dollars ($10,000.00), including, but not limited to, the costs of administration of the Agreement, shall be subject to the examination and audit of the State Auditor at the request of the District or as part of any audit of the District for a period of three (3) years after final payment is made under the Agreement.  In connection with any such audit, the District and/or the State Auditor shall have access to the Contractor’s facilities, shall be allowed to interview all of the Contractor’s current or former employees to discuss matters pertinent to the performance of the Agreement, shall have access to all necessary records, and shall be provided adequate and appropriate work space, in order to conduct audits in compliance with this Section 10.2.  Without limiting the generality of the foregoing:

    - Purpose of Examination and Audit.  The District and the Auditor General shall have the right to perform the examinations and audits which are the subject of this Section 10.2 for the purpose of determining whether and to what extent: (a) the Contractor and Subcontractors have performed the Work in compliance with Applicable Laws; (b) the Contractor has otherwise complied with the terms and conditions of the Project Documents; and (c) the Contractor is entitled to receive payments requested by the Contractor relative to the Agreement.

    - Place of Audit and Examination.  Examinations and audits hereunder may be conducted at the Contractor’s principal offices during the Contractor’s regular business hours, or at such other reasonable times and places determined by the District and/or the Auditor General.  Where the examinations and audits are conducted at the Contractor’s offices (or at those of the Contractor’s Subcontractors, material suppliers or insurers), the Contractor shall provide (or cause said parties to provide) the District and the Auditor General with appropriate work space necessary to allow the District and the Auditor General to conduct the audits and examinations in compliance with this Section 10.2.

    - Records Subject to Audit.  The Contractor’s, Subcontractors’, material suppliers’ and insurers’ records which are subject to audit hereunder shall include any and all information, documentation, materials and data of every kind and character relative to the Project or the Project Documents, including without limitation: books and records; papers; subscriptions; recordings; agreements; purchase orders; leases; contracts; subcontracts (including proposals of successful and unsuccessful bidders, bid recaps and similar documents); commitments; notes; daily diaries; superintendent reports; drawings; receipts; vouchers; memoranda; original estimates; estimating worksheets; correspondence; change order files (including documentation of negotiated settlements); back-charge logs and supporting documentation; general ledger entries detailing cash and trade discounts earned, insurance rebates and dividends; and any other supporting evidence deemed necessary by the District and/or the Auditor General to carry out the purposes of the examination and audit (collectively, the “Auditable Records”).

    - Format of Auditable Records.  The District and the Auditor General shall have the right to obtain both paper copies and (if available) computer readable data copies of the Auditable Records identified in Section 10.2.3.

    - Employee Interviews.  In connection with the examinations and audits conducted under this Section 10.2, the District and the Auditor General, during the term of the Agreement and for a period of three years after final payment has been made there under (or longer if required by law), shall each: (a) have access to the Contractor’s (and its Subcontractors’ material suppliers and insurers) facilities; and (b) be allowed to interview all current and former employees of the Contractor (and its Subcontractors’ material suppliers and insurers) to discuss matters pertinent to the performance of the Agreement.

    - Applicability to Third Parties.  The Contractor shall require all of its Subcontractors, material suppliers’ and insurance agents to comply with provisions of this Section 10.2 by insertion of the requirements hereof in each written contract between said parties and the Contractor.  The Contractor will cooperate fully and will cause all such parties to cooperate fully in furnishing or in making available to the District and the Auditor General from time to time whenever requested in an expeditious manner any all Auditable Records (as defined in Section 10.2.3) .in the possession of such parties requested by the District or the Auditor General.

    - Cost of Audit or Examination.  If an audit or examination in accordance with this Section 10.2 discloses overcharges (of any nature) by the Contractor to the District in excess of one-half of one percent (.5%) of the total contract billings under the Agreement, the reasonable actual cost of the audit or examination shall be reimbursed to the District by the Contractor.

    - Overpayments or Underpayments Disclosed by Audit or Examination.  If any audit or inspection conducted hereunder discloses any overpayment or underpayment made by the District to the Contractor under the Agreement, then within a reasonable amount of time (not to exceed 90 calendar days) from presentation of the District or Auditor General of its findings to the Contractor, (a) the District shall pay any shortfall to the Contractor, and (b) the Contractor shall refund any overpayment to the District.

  - Drawings Reflecting Actual Construction.  During the course of construction, the Contractor shall maintain drawings kept up each day to show the Project as it is actually constructed.  Every sheet of the Plans and Specifications which differs from the actual construction shall be marked and sheets so changed shall be noted on the title sheets of the Plans and Specifications.  All change orders shall be shown by reference to sketch drawings, and any supplementary drawings or change order drawings shall be included.  The Contractor shall review the “as-built” drawings with the Construction Inspector at least once a month to demonstrate that all changes that have occurred are being fully and accurately recorded.  All “record” drawings of the Work shall be prepared by an appropriate engineer approved by the Architect.

  - Records Related to Change Orders.  The Contractor shall maintain all records relating to costs in connection with change orders, as required by Section 16.3.8 below.

  - Payroll Records.

    - Contractor Must Keep Accurate Payroll Records.  Pursuant to the provisions of Labor Code Section 1776, the Contractor shall keep and shall cause each subcontractor performing any portion of the work under the Agreement to keep an accurate payroll record, showing the name, address, social security number, work classification, straight time and overtime hours worked each day and week, and the actual per diem wages paid to each journeyman, apprentice, worker, or other employee employed by the Contractor in connection with the work.

    - Inspection of Payroll Records.  The payroll records enumerated under Section 10.5.1 above shall be certified and shall be available for inspection at all reasonable hours at the principal office of the Contractor on the following basis:

      - A certified copy of an employee’s payroll record shall be made available for inspection or furnished to the employee or his or her authorized representative on request.

      - A certified copy of all payroll records enumerated in Section 10.5.1 above shall be made available for inspection or furnished upon request to a representative of the District, the Division of Labor Standards Enforcement, and the Division of Apprenticeship Standards of the Department of Industrial Relations.

      - A certified copy of all payroll records enumerated in Section 10.5.1 above shall be made available for inspection upon request by the public or copies thereof made; provided, however, that a request by the public shall be made through either the District, the Division of Apprenticeship Standards, or the Division of Labor Standards Enforcement.  If the requested payroll records have not been provided pursuant to this Section 10.5.2, the requesting party shall, prior to being provided the records, reimburse the costs of preparation by the Contractor, subcontractors, and the entity through which the request was made.  The public shall not be given access to the records at the principal office of the Contractor.

      - The form of certification shall be as follows:

I, 				 (printed name), the undersigned, am 						 (position in business) with the authority to act for and on behalf of 							 (Name of business and/or name of the Contractor), certify under penalty of perjury that the records or copies thereof submitted and consisting of 						 (description and number of pages) are the originals or true, full and correct copies of the originals which depict the payroll record(s) of the actual disbursements by way of cash, check, or whatever form to the individual or individuals named.

Dated: 			 Signature:

    - Filing Certified Copies With Requesting Entities.  Contractor shall file a certified copy of the payroll records enumerated in Section 10.5.1 above with the entity that requested the records within five (5) days after receipt of a written request.  In the event that the Contractor fails to comply within the five (5) day period, the Contractor shall, as a penalty to the District, forfeit One Hundred Dollars ($100) for each calendar day, or portion thereof, for each worker, until strict compliance is effectuated.  Upon the request of the Division of Apprenticeship Standards or the Division of Labor Standards Enforcement, these penalties shall be withheld from progress payments then due.

    - Non-Disclosure of Confidential Employee Information.  Any copy of payroll records made available for inspection as copies and furnished upon request to the public by the District, the Division of Apprenticeship Standards, or the Division of Labor Standards Enforcement shall be marked or obliterated in such a manner as to prevent disclosure of an individual’s name, address, and social security number.  The name and address of the Contractor shall not be marked or obliterated.

    - Location of Payroll Records.  The Contractor shall inform the District of the location of the payroll records enumerated in Section 10.5.1 above, including the street address, city and county, and shall, within five (5) working days, provide a written notice of a change of location and address.

    - Responsibility for Compliance.  It shall be the responsibility of the Contractor to ensure compliance with the provisions of this Section 10.5 and the provisions of Labor Code Section 1776.

- HAZARDOUS MATERIALS, ASBESTOS, AND DIFFERING CONDITIONS

  - Hazardous Materials.  Neither the Contractor, any Subcontractor, nor any of their material suppliers shall use or bring upon the Project site any Hazardous Materials, except in compliance with all applicable Hazardous Materials Laws.  As used herein, the term “Hazardous Materials” means any hazardous or toxic substance, material, or waste which now is or hereafter becomes regulated by any local governmental authority, the State of California or the United States Government.  The term “Hazardous Material” includes, without limitation, any material or substance which is (i) defined as “Hazardous Waste,” “Extremely Hazardous Waste,” or “Restricted Hazardous Waste” under Sections 25115, 25117 or 25122.7, or listed pursuant to Section 25140, of the California Health and Safety Code, Division 20, Chapter 6.5 (Hazardous Waste Control Law), (ii) defined as a “Hazardous Substance” under Section 25316 of the California Health and Safety Code, Division 20, Chapter 6.8 (Carpenter-Presley-Tanner Hazardous Substance Account Act), (iii) defined as a “Hazardous Material,” “Hazardous Substance,” or “Hazardous Waste” under Section 25501 of the California Health and Safety Code, Division 20, Chapter 6.95 (Hazardous Materials Release Response Plans and Inventory), (iv) defined as a “Hazardous Substance” under Section 25281 of the California Health and Safety Code, Division 20, Chapter 6.7 (Underground Storage of Hazardous Substances), (v) petroleum, (vi) asbestos, (vii) listed under Article 4 of Title 22 of the California Code of Regulations, Division 4.5, Chapter 11, or defined as a hazardous or extremely hazardous waste under Article 2 of Title 22 of the California Code of Regulations, Division 4.5, Chapter 10 (viii) designated as a “Hazardous Substance” pursuant to Section 311 of the Federal Water Pollution Control Act (33 U.S.C. § 1321), (ix) defined as a “Hazardous Waste” pursuant to Section 1004 of the Federal Resource Conservation and Recovery Act, 42 U.S.C. § 6921 et seq. (42 U.S.C. § 6903), or (x) defined as a “Hazardous Substance” pursuant to Section 101 of the Comprehensive Environmental Response, Compensation and Liability Act, 42 U.S.C. § 9601 et seq. (42 U.S.C. § 9601).

  - Asbestos.

    - Non-Utilization of Asbestos-Containing Material.  Neither the Contractor nor any Subcontractor shall use or install any asbestos-containing materials in the Project.  Upon the District’s request, the Contractor will be required to execute and submit a “Certificate Regarding Non-Asbestos-Containing Materials” in form and content acceptable to the District.  Should asbestos-containing materials be installed by the Contractor in violation of that certification, then the Contractor shall bear the entire cost of such removal, including without limitation the cost of the District’s asbestos removal contractor, the cost of the District’s asbestos consultant, analytical and laboratory fees, time delays and additional costs as may be incurred by the District.

    - Contractor’s Work Which Affects Existing Asbestos.  If the Contractor performs Work in such a manner that it affects existing asbestos-containing materials at the Project site, the Contractor does so at its own risk and discretion with full knowledge of the currently accepted standards, hazards, risks and liabilities associated with asbestos work and asbestos-containing products.  The Contractor shall instruct its employees and Subcontractors with respect to those standards, hazards, risks and liabilities.

    - Removal of Asbestos.  Removal of asbestos-containing materials shall be done in accordance with the following criteria:

      - Decontamination and removal of Work found to contain asbestos or Work installed with asbestos-containing equipment shall be done only under the supervision of a qualified consultant, knowledgeable in the field of asbestos abatement and accredited by the California Environmental Protection Agency.

      - The asbestos removal contractor shall be a contractor accredited by the California Environmental Protection Agency and qualified in the removal of asbestos and shall be chosen and approved by the District’s asbestos consultant, who shall have sole discretion and final determination in this matter.

      - The asbestos consultant shall be chosen and approved by the District, which shall have sole discretion and final determination as to that selection.

      - The Work will not be accepted until asbestos contamination is reduced to levels deemed acceptable by the District’s asbestos consultant.

  - Discovery of Hazardous Materials.  If the Contractor encounters on the site material reasonably believed to be Hazardous Materials, the Contractor shall immediately stop Work in the area affected and report the condition to the Construction Manager in writing.  The Work in the affected area shall not thereafter be resumed except by written agreement of the District and the Contractor.

  - Discovery of Differing Conditions.  The Contractor shall promptly notify the Construction Manager in writing of If the Contractor discovers any subsurface or latent physical conditions at the Project site which are different from those indicated in the Project Documents, or if the Contractor discovers any physical conditions at the Project site of an unusual nature or materially different from those ordinarily encountered and generally recognized as inherent in Work of the character provided for in the Agreement, then the Contractor shall promptly deliver written notice to the Construction Manager of that discovery.  Such notice shall be delivered before the conditions are disturbed and in no event later than five (5) days following the Contractor’s discovery of those conditions.

  - District’s Investigation of Contractor’s Report of Hazardous Materials or Differing Conditions.  Upon the Construction Manager’s receipt of a notice from the Contractor pursuant to Sections 11.3 and 11.4 above, the Construction Manager shall forward that notice to the District, and the District shall promptly investigate the material or conditions.  If the District finds that the conditions do materially so differ, or do involve Hazardous Materials, and cause a decrease or increase in the Contractor’s cost of, or the time required for, performance of any part of the Work shall issue a change order pursuant to Article 16 below.  If a dispute arises between the District and the Contractor as to whether the conditions materially differ or involve Hazardous Materials, or cause a decrease or increase in the Contractor’s cost of, or time required for, performance of any part of the Work, then the Contractor shall not be excused from any scheduled completion date provided for by the Project Documents, but shall proceed with all the Work to be performed under the Project Documents.  The Contractor shall retain any and all rights provided either by contract or by law which pertain to the resolution of disputes and protests between the contracting parties, pursuant to Public Contract Code Section 7104.

  - Material Safety Data Sheets (MSDS).  The Contractor is required to ensure Material Safety Data Sheets are available in a readily accessible place at the work site for any material requiring a Material Safety Data Sheet per the Federal “Hazard Communication” standard, or employees right to know law.  The Contractor is also required to ensure proper labeling on any substance brought onto the job site and that any person working with the material or within the general area of the material is informed of the hazards of the material and follows property handling and protection procedures.  Two additional copies of the Material Safety Data Sheets must also be submitted directly to the Construction Manager.

- SHOP DRAWINGS

  - Overview of Shop Drawing Procedures.  The Contractor shall check and verify all field measurements and shall submit to the Architect (through the Construction Manager) within twenty (20) calendar days of the date specified on the Notice to Proceed a detailed list of activities required for mobilization and start of construction that includes all shop drawings, schedules, and materials list required for the work of various trades.  All lists should be consistent within requirements as stated in Article 5 CONSTRUCTION SCHEDULES, and PROCEDURES MANUAL SECTION 1305. The Architect shall review such drawings, schedules and materials list only for conformance with design concept of Project and compliance with information given in Project Documents, and return as approved or disapproved with guidance as to required corrections within thirty five (35) calendar days.  The Contractor shall make any corrections required by the Architect, file three (3) corrected copies with the Architect (through the Construction Manager), and furnish such other copies as may be needed for construction within ten (10) calendar days.  The Architect’s approval of such drawings, schedules, or materials list shall not relieve the Contractor from responsibility for deviations unless the Contractor has in writing called the Architect’s attention to such deviations at time of submission and secured the Architect’s written approval, nor shall it relieve the Contractor from responsibility for errors in shop drawings or schedules.  Shop drawings, and all revisions thereto, must be submitted by the Contractor at a time sufficiently early to allow review of same by the DSA if required, and the Architect, and to accommodate the rate of construction progress required under the Project Documents.  The Contractor will be required to pay the Architect’s reasonable and customary fees in order to expedite review of shop drawings which are not submitted in a timely fashion.

  - Shop Drawings Shall Conform to Plans and Specifications.  All submittals of shop drawings, catalog cuts, data sheets, schedules and material lists shall be complete and shall conform to contract drawings and specifications.

  - Definition of “Shop Drawings”.  The term “shop drawing” as used herein shall be understood to include, but not be limited to, detail design calculations, fabrication and installation drawings, lists, graphs and operating instructions.

  - Transmittal Form.  All shop drawing submittals shall be accompanied by an accurately completed transmittal form using the format designated by the District.  Any shop drawing submittal not accompanied by such a form, or where all applicable items on the form are not completed, will be returned for re-submittal.  Normally, a separate transmittal form shall be used for each specific item or class of material or equipment for which a submittal is required.  Transmittal of shop drawings on various items using a single transmittal form will be permitted only when the items taken together constitute a manufacturer’s “package” or are so functionally related that expediency indicates review of the group or package as a whole.  At its option, the Contractor or Supplier may obtain from the Architect quantities of the shop drawing transmittal form at reproduction cost.

  - Material and Equipment Suppliers.  The Contractor may authorize a material or equipment supplier to deal directly with the Construction Manager with regard to shop drawings, however, ultimate responsibility for the accuracy and completeness of the information contained in the submittal shall remain with the Contractor.

  - Contractor’s Stamp Approving Shop Drawings.  The Contractor’s review and approval of shop drawings shall include the following stamp:

“The Contractor has reviewed and approved not only the field dimensions but the construction criteria and has also made written notation regarding any information in the shop drawings that does not conform to the Project Documents.  This shop drawing has been coordinated with all other shop drawings received to date by the Contractor and this duty of coordination has not been delegated to subcontractors, material suppliers, the Architect, or the engineers on this project.

___________________________________________

Signature of the Contractor”

  - Architect’s Review of Shop Drawings.  The Architect’s review of shop drawings will be limited to checking for general agreement with the Project Documents.  The Architect’s review shall in no way relieve the Contractor of responsibility for errors or omissions contained therein, nor shall such review operate to waive or modify any provision contained in the Project Documents.  Fabricating dimensions, quantities of material, applicable code requirements, and other contract requirements shall be the Contractor’s responsibility.  Within fourteen (14) calendar days after receipt of shop drawings, the Architect will (through the Construction Manager) return one or more prints of each drawing to the Contractor with the Architect’s comments noted thereon.  If prints of the shop drawing are returned to the Contractor marked “NO EXCEPTIONS TAKEN,” formal revision of said drawing will not be required.  If prints of the drawing are returned to the Contractor marked “MAKE CORRECTIONS NOTED,” formal re-submittal of said drawings will not be required.  If prints of the drawing are returned to the Contractor marked “REVISE AND RESUBMIT,” the Contractor shall revise said drawing and shall resubmit six (6) copies of the revised drawing to the Architect (through the Construction Manager).  If prints of the drawing are returned to the Contractor marked “REJECTED RESUBMIT,” the Contractor shall resubmit six (6) new copies of the drawing to the Architect.

  - Contractor’s Re-Submittal of Shop Drawings.  The Contractor shall make a complete and acceptable submittal to the Architect by the second submission of drawings.  The District shall withhold funds due the Contractor to cover additional costs of the Architect’s review beyond the second submission and any other costs incurred by the District.

  - No Work or Fabrication If Shop Drawings Must Still Be Resubmitted.  Fabrication of an item shall not be commenced before the Architect has reviewed the pertinent shop drawings and returned copies to the Contractor marked with “NO EXCEPTIONS TAKEN,” or “MAKE CORRECTIONS NOTED.”  No Work represented by required shop drawings shall be purchased or commenced until the applicable submittal has been approved.  The Work shall conform to the approved shop drawings and all other requirements of the Project Documents.  The Contractor shall not proceed with any related Work which may be affected by the Work covered under shop drawings until the applicable shop drawings have been approved, particularly where piping, machinery, and equipment and the required arrangements and clearances are involved.

  - Revisions on Shop Drawings Are Not Grounds for Claims for Extra Work.  Revisions indicated on shop drawings shall be considered as changes necessary to meet the requirements of the Project Documents and shall not be taken as the basis of claims for extra work.

  - Simultaneous Submission of Related Shop Drawings.  Except where the preparation of a shop drawing is dependent upon the approval of a prior shop drawing, all shop drawings pertaining to the same class or portion of the Work shall be submitted simultaneously.

  - DSA Approval of Shop Drawings and Deferred Approval Items.  Calculations of a structural nature contained in the Shop Drawings, as well as all Deferred Approval items identified in Section 01411 of the Specifications, must be approved by the DSA.  Shop drawings, Deferred Approval items, and all revisions thereto, must be submitted by the Contractor to the Construction Manager at a time sufficiently early to allow review of same by the DSA.

  - Limitation on Contractor’s Claims Relative to Shop Drawings.  The Contractor shall have no claim for damages or extension of time due to any delay resulting from the Contractor having to make the required revisions to shop drawings unless review by the Architect of said drawings is delayed beyond the time provided hereinbefore and the Contractor can establish that the Architect’s delay in review actually resulted in a delay in the Construction Schedule approved by the District.  The Contractor shall not be entitled to any claim for damages resulting from DSA review extending beyond fifteen (15) calendar days after submittal; however, the District may consider an extension of time due to any delay caused by DSA review.

- SAMPLES

  - Contractor’s Duty to Provide Samples.  The Contractor shall furnish to the Construction Manager for the Architect’s approval, within twenty (20) calendar days following the Notice to Proceed, all samples as required in the Specifications, together with catalogs and supporting data required by the Architect.  This provision shall not authorize any extension of time for performance of the Work.  The Architect shall review such samples, as to conformance with design concept of Work and for compliance with information given in Project Documents and approve or disapprove same within ten (10) working days from receipt of same.

  - Standards.  Unless specified otherwise, sampling, preparation of samples and tests shall be in accordance with the latest standards of the American Society for Testing and Materials.

  - Testing.  Samples shall, upon demand of the Architect, the Construction Manager or the District, be submitted for tests or examinations and considered before incorporation of same into the Work.  The Contractor shall be solely responsible for delays due to samples not being submitted in time to allow for tests.  Acceptance or rejection will be expressed in writing.  Work shall be equal to approved samples in every respect.  Samples which are of value after testing will remain the property of the Contractor.

- CONTRACT TIME

  - Commencement and Completion Dates.  The District shall designate in the Notice to Proceed the commencement date, on which the Contractor shall immediately begin and thereafter diligently prosecute the Work to completion.  The Contractor agrees to complete the Work on the Contractual Completion Date, unless the Contractual Completion Date is adjusted, in writing, by a change order signed by the District.  The Contractor may complete the Work before the Contractual Completion Date if (a) doing so will not interfere with the District or the District’s other contractors engaged in related or adjacent activities and (b) the District agrees in writing to such early completion.  In requesting to complete the Work ahead of schedule, the Contractor may be responsible for additional management fees from the District’s consultants if the District determines that it will incur such additional fees, but in that event the District shall not grant its approval until the District and the Contractor have agreed upon the amount of such additional fees.  For purposes of this Section, the Work shall be regarded as completed only when accepted as complete by an action of the District’s School Board pursuant to Section 8.3 above.

  - Adjustment Of Completion Date Due to Unforeseeable or Uncontrollable Acts.  The Contractor shall not be assessed with liquidated damages, nor with the cost of engineering and inspection, during any delay in the completion of the Project caused by acts of God, the public enemy, fire, flood, epidemic, quarantine restriction, strike, freight embargo, discovery of archaeological or pale ontological artifacts, and unusual action of the elements, provided that the Contractor notifies the Construction Manager in writing of the causes of delay within three (3) days from the beginning of any such delay.  The Architect, in conjunction with District and the Construction Manager, shall determine the facts with regard to the delay and the reasonable period of time by which the date of completion should be extended by reason thereof, if any, and advise the District.  District’s findings thereon shall be final and conclusive.  There shall be no compensation to the Contractor for costs associated with this kind of delay.  As used herein, the term “unusual action of the elements” is limited to extraordinary, adverse weather conditions or conditions immediately resulting there from which cause a cessation in the progress of the Work and which delay the time of completion of the Work.

  - No Adjustment Based on Normal Weather or Industrial Conditions.  The Contractor shall have no rights to an adjustment in the Contractual Completion Date due to weather conditions or industrial conditions which are normal for Orange County, California.  The Contractual Completion Date has been calculated with consideration given to the average climate range and usual industrial conditions prevailing in Orange County, California.

  - Delays Caused by District or Architect.  If the Contractor is delayed in completing the Work by reasons of any act of the Architect or the District which is prohibited in the Agreement, or by reason of changes made pursuant to Article 16 without agreement being reached as to any extension of the Contractual Completion Date, the Contractor shall notify the Construction Manager in writing of the causes of the delay within three (3) days from the beginning of the delay.

  - Substantiation of Delay.  Promptly following each notice of delay delivered by the Contractor under this Article 14, the Contractor shall provide the Construction Manager with documentation and justification to substantiate the delay and its relation to the Project’s critical path.

  - Liquidated Damages.  The Contractor and the District hereby agree that the exact amount of damages for failure to complete the Work by the Contractual Completion Date is extremely difficult or impossible to determine.  It is therefore agreed that the Contractor will pay the District the sum of money stipulated per day in Section 5 of the Agreement for each day’s delay in completing the work beyond the time prescribed.  A final credit change order shall be executed to assess liquidated damages.  If the Contractor fails to pay liquidated damages, the District may deduct the amount therefore from any money due or that may become due to the Contractor under the contract.

  - Time is of the Essence.  All time limits specified in the Agreement and the other Project Documents are of the essence of the Contract.

- REQUESTS FOR INFORMATION

  - Architect’s Response to Requests for Interpretation, Clarification or Instructions.  Following a request by the Contractor for interpretation, clarification or instructions as to the Project Documents, the Architect, with review as required by the Construction Manager and the District, shall, within a reasonable time, issue in writing the interpretation, clarification, or additional detailed instructions requested and in accordance with Section 01305-6.  Should any details be more elaborate, in the opinion of the Contractor, than scale drawings and specifications warrant, the Contractor shall give written notice thereof to the Construction Manager within three (3) days after the Contractor’s receipt of same.  If no such notice is given to the Construction manager within that time, the details will be deemed a reasonable development of the scale drawings.  If such notice is timely given, and if the Architect agrees with the Contractor’s opinion, then the Architect will either modify the drawings pursuant to Section 4.14 above or shall recommend to the District a change order of the extra work required by the additional detail pursuant to Article 16 below.

  - Procedure Where Contractor Believes a Response to a Request for Information Expands the Scope of Work.  If the Contractor believes that any interpretation, clarification, or additional detailed instructions calls for the Contractor to perform Work beyond the scope of work specified in the Agreement, then the Contractor must submit written notice thereof to the District, the Architect, the Inspector(s) and the Construction Manager within three (3) calendar days following receipt of such interpretation, clarification, or additional detailed instructions (and in any event prior to commencement of Work thereon).  That notice shall be accompanied by a detailed cost breakdown relative to the additional Work claimed (including without limitation an explanation of any delay impacts related to the claim).  If after considering such notice, claim and accompanying material the Architect agrees with the Contractor, the Architect shall either (a) revise its interpretation, clarification or detailed instructions, or (b) authorize the extra Work by a contract change order or by a field instruction with a change order to follow.  If the Architect disagrees (and is unable to convince the Contractor that the scope of work has not been increased), the Contractor shall nevertheless perform such Work upon receipt from the District of a written order to do so.  At the conclusion of each day in which the Contractor has performed any of the disputed Work, the Contractor shall prepare (and the Inspector shall verify) time and material records for that day.  In such case, the Contractor shall have the right to have the claim later determined pursuant to  below.  The Contractor shall have no claim for additional compensation because of such interpretation, clarification, or additional detailed instructions, unless the Contractor gives the written notice required by this Section 15.2.

  - Improper Requests for Information.  If the Architect determines that any request by the Contractor for clarification or interpretation is not justified or does not reflect adequate and competent supervision and/or knowledge by the Contractor and/or its Subcontractors, then the Contractor shall pay the reasonable and customary fees incurred by the Architect in processing and responding to the request.

- CHANGES TO THE WORK

  - Change Orders in General.

    - District’s Right to Issue Change Orders.  The District reserves the right to issue written change orders directing changes in the Agreement at any time prior to the acceptance of the Work without voiding the Agreement, and the Contractor shall promptly comply with each and every such change order.  The Contractor may request changes in the Work, but shall not act on the changes until approved in writing by the District.  Any changes made without authority in writing from the District shall be the responsibility of the Contractor, and no increase in compensation or time extension will be made for a change involving greater expense to the Contractor, and changes involving greater or lesser expense may be rejected by the District with the consequent responsibility on the Contractor to at his own expense replace the changed work with that originally specified.

    - Adjustment of Contract Price Based on Change Orders.  On the basis set forth herein, the Contract Price shall be adjusted for any change order requiring a different quantity or quality of labor, material or equipment from that originally required, and the partial payments to the Contractor, set forth in Section 21.5 below, shall be adjusted to reflect the change.  Whenever the necessity for a change arises, and when so ordered by the District in writing, the Contractor shall take all necessary steps to halt such other Work in the area of the change that might be affected by the change.  Changed Work shall be performed in accordance with the original requirements of the Agreement except as modified by the change order.  Except as provided in this Article 16, the Contractor shall have no claim for any compensation due to changes in the Work.

  - Proposed Change Orders.

    - Cost Request Bulletin.  The Architect, with the approval of the District, may from time to time issue to the Contractor (delivered through the Construction Manager) a cost request bulletin for a proposed change order.

    - Contractor’s Response to Cost Request Bulletin.  Within seven (7) calendar days after issuance of the cost request bulletin, the Contractor shall respond by delivering to the Construction Manager the following information: (a) the amount which the Contractor proposes should be added to or subtracted from the Contract Price due to the proposed change order; (b) a detailed cost estimate prepared by the Contractor which supports that proposed price adjustment; (c) any adjustment to the time periods and deadlines for commencement, performance and/or completion of all or any part of the Work that the Contractor believes will be necessitated by and directly attributable to the proposed change order; and (d) a detailed explanation substantiating the Contractor’s proposed time adjustment.  The amount which the Contractor proposes to add or subtract from the Contract Price should include any and all of the Contractor’s expenses in connection with the proposed change, because the Contractor will not be entitled to receive any additional compensation in connection with the proposed change order other than the increased amounts determined pursuant to this Article 16.  The Contractor’s failure to request an adjustment of the Contract Price when responding to the cost request bulletin shall waive any right to subsequently claim an adjustment of the Contract Price in connection with the changed Work.  The Contractor’s failure to request an adjustment of time when responding to the cost request bulletin shall waive any right to subsequently claim an adjustment of the time for final completion of the changed Work.  The District shall not bear any cost incurred by the Contractor in acquiring information relative to a proposed change order and/or a cost request bulletin.

    - District Review of Contractor’s Response.  Upon its receipt of the Contractor’s response to the cost request bulletin, the Construction Manager shall deliver that response to the Architect.  The Architect will review that response and advise the District, which will make the final decision as to whether the change is to be made and as to the amounts (if any) of any adjustment to the Contract Price and time periods to be allowed by the District in connection with the change.  Upon request by the District in connection with the Contractor’s response to the cost request bulletin, the Contractor shall permit the District (and the Architect and the Construction Manager) to inspect the original estimate of the anticipated costs of performing the Work that the Contractor used in submitting its bid for the Project, and shall also permit the District (and the Architect and the Construction Manager) to review subcontracts and purchase orders relating to the proposed change order and/or to the Contractor’s response to the cost request bulletin.

    - Issuance of Change Order.  In situations where the District and the Contractor agree on the amount to be added to be added to or deducted from the Contract Price and the time to be added to or deducted from the time available to commence, perform and complete the Work, the District shall cause the Architect to prepare a change order, which shall be signed by the District, the Architect and the Contractor.  Once the change order has been fully signed, the Contractor shall proceed with the changed Work (unless a different commencement date is specified in the change order).

    - Commencement of Changed Work in Absence of Agreement.  If the District and the Contractor are unable to agree upon an adjustment to the Contract Price or upon a time adjustment in connection with the changed Work proposed by the cost request bulletin, the Contractor shall (upon notice from the District delivered by the Construction Manager) proceed with the changes pursuant to the provisions of Sections 16.4 and 16.5 below, reserving the right as indicated below to further pursue its claim for a time adjustment or Contract Price adjustment.

    - Commencement of Changed Work If Contractor Fails to Respond to Cost Request Bulletin.  If the Contractor fails to respond to the cost request bulletin within the time and in the manner specified above, and if the Contractor has not obtained (through the Construction Manager) the District’s permission for a delay in submission (which permission the District may grant or deny in its sole discretion), then the District may order the Contractor in writing to begin the work immediately, and the Contract Price shall be adjusted in accordance with District’s estimate of cost, unless the Contractor within fifteen (15) days following the completion of the changed Work presents proof convincing to the District that the District’s estimate is in error.

    - Commencement of Changed Work in Emergencies.  Notwithstanding anything to the contrary set forth in this Article 16, the District may require the Contractor to proceed immediately with any changes to Work where, in the District’s opinion, an emergency situation exists requiring immediate commencement of such changes, in accordance with Section 7.10.3 above.

  - Allowable Costs In Connection With Change Orders.  The only estimated or actual costs which will be allowed because of changed work, and the manner in which such costs shall be computed, are as follows:

    - Labor.  Costs are allowed for the actual payroll cost to the Contractor for labor, field supervision (but not field office supervision), and engineering or technical services directly required for the performance of the changed work (but not site management such as field office estimating, clerical, engineering, or management), including payments, assessments, or benefits required by lawful labor union collective bargaining agreements, compensation insurance payments, contributions made to the State pursuant to the Unemployment Insurance Code, and for taxes paid to the federal government required by the Social Security Act of August 14, 1935, as amended.  No labor coast will be recognized at a rate in excess of prevailing wage in the locality at the time the work is performed, nor will the use of a classification which would increase the labor cost be permitted unless the Contractor establishes to the satisfaction of the District the necessity for payment at a higher rate, unless otherwise stipulated by the PSA.

    - Materials.  Costs are allowed for the cost to the Contractor for the materials directly required for the performance of the changed Work.  Such cost of materials may include the costs of procurement, transportation, sales tax, and delivery if necessarily incurred.  If a trade discount by the actual supplier is available to the Contractor, it shall be credited to the District.  If the materials are obtained from a supply or source owned wholly or in part by the Contractor, payment therefore will not exceed the current wholesale price of such material.  If, in the opinion of the District, the cost of materials is excessive, or if the Contractor fails to furnish satisfactory evidence of the cost from the actual supplier thereof, then in either case the cost of the materials shall be deemed to be the lowest wholesale price at which similar materials are available in the quantities required at the time they were needed.  The District reserves the right to furnish such materials, as it deems advisable and the Contractor shall have no claim for costs or profit on material furnished by the District.

    - Equipment.

      - Costs are allowed for the actual cost to the Contractor for the use of equipment directly required in the performance of the changed work except that no payment will be made for time while equipment is inoperative due to breakdowns or non-working days.  The rental time shall include the time required to move the equipment to the Project site from the nearest available source for rental of such equipment, and to return it to the source.  If such equipment is not moved by its own power, then loading and transportation costs will be paid.  However, neither moving time nor loading and transportation costs of will be paid if the equipment is used on the Project in any other way than upon the changed work.  Individual pieces of equipment having a replacement value of $100.00 or less shall be considered to be tools or small equipment, and no payment therefore will be made.

      - For equipment owned, furnished or rented by the Contractor, no cost therefore shall be recognized in excess of the rental rates established by the distributors or rental agencies in the locality where the is work is performed.

      - The amount to be paid by the Contractor including mark–up for the use of equipment as set forth above shall constitute full compensation to the Contractor for the cost of fuel, power, oil, lubrication, supplies, small tools, small equipment, necessary attachments, repairs and maintenance of any kind, depreciation, storage, insurance, labor (except for equipment operators who shall be paid for as provided in Section 16.3.1 above), and any and all costs to the Contractor incidental to the use of such equipment.

    - Work by Subcontractors and Vendors.  . For any portion of the changed Work which is performed by a Subcontractor, the Contractor shall furnish to the District a detailed estimate, in conformance with the Proposed Cost Change Form provided in these General Conditions, prepared and signed by the Subcontractor of the cost to the Subcontractor for performing the Changed Work. The combined costs for subcontractors overhead, profit, taxes, indirect supervision, insurance, bonds, and any other costs not allowed by the Article 16 shall not exceed fifteen percent (15%).  The aggregate mark-ups allowed by multi-tiered subcontractors shall not exceed twenty-six percent (26%). Estimates of the to be deleted from the Subcontractor’s portion of the work shall be the gross cost of the deducted Work plus at least six percent (5%) for overhead, bond, insurance, and related savings. The Contractor shall be entitled to no more than five percent (5%) of the mark-up for Subcontractor performed work or on material or vendor invoices.

- For the changed Work to be furnished by a vendor, the Contractor shall furnish upon demand of the District, a lump sum estimate of the costs of the items including taxes and cartage to the Contractor prepared by the vendor. No vendor mark-up for overhead, profit, layout, supervision or bonds will be allowed for changed work furnished by a vendor.

    - General Contractor’s Mark-Up for Added Work. When changed work is self-performed by the Contractor, the Contractor may add to the total cost estimates for such work no more than fifteen percent (15%) of profit, overhead, insurance, taxes, indirect supervision, binds, and any other costs allowed by this Article 16 and in accordance with the Proposed Cost Change Form provided in these General Conditions. However, the General Contractor shall be entitled to no more than five percent (5%) of the mark-up if a Subcontractor performed the work. Refer to Section 7.8.3 above for limitations upon increased costs relative to utility lines.

    - Credit for Deleted Work.  Where an entire item or section of Work is deleted from the Contract, the entire subcontract costs bid cost shall be considered the appropriate deduction less the value of Work performed, and shall have at least five percent (5%) mark-up added thereto for the Contractor’s saved overhead, bonds, insurance, and taxes.  If subcontract cost or bid cost is not identifiable, then estimates of the amount to be deducted from the Contract Price shall be the gross cost of the deducted work plus at least five percent (5%) for saved overhead, bonds, insurance, and taxes.  For proposed change orders, which involve both added and omitted Work, the Contractor shall separately estimate the cost of the added Work before mark-ups, and separately estimate the cost of the omitted Work before allowance of a credit.  If the difference between the costs results in the increase to the Contract Price, the mark-up for added Work shall be applied to the difference, and if the difference in the costs results in a decrease, then the mark-up for deleted Work shall be applied to the difference.

    - Market Values.  Cost for added Work shall be no more than market values prevailing at the time of the change, unless the Contractor can establish to the satisfaction of the District that it investigated all possible means of obtaining Work at prevailing market values and that the excess cost could not be avoided.

    - Contractor Must Keep Records Substantiating Costs of Changed Work.  The Contractor must keep and submit to the Inspector for verification time and material records substantiating the Contractor’s costs in connection with the performance of Work required by change orders.  The Contractor shall deliver copies thereof to the Construction Manager upon request, together with such other proof reasonable requested by the District of the Contractor’s costs.

### 16.3.9	Format for Proposed Cost Change.  The following format shall be used as applicable by the District and the Contractor to communicate proposed additions and deductions to the Contract.  A copy of a proposed Construction Change Directive form is provided at the end of this Article.

|  | EXTRA | CREDIT |
| --- | --- | --- |
| (a) Material (attach itemized quantity and unit cost plus sales tax) | ________ | ________ |
| (b) Labor (attach itemized hours and rates) | ________ | ________ |
| (c) Equipment (attach invoices) | ________ | ________ |
| (d) Subtotal | ________ | ________ |
| (e) If Subcontractor performed Work, add Subcontractor’s overhead and profit to portions performed by Sub-contractor, not to exceed fifteen percent (15%) of item (d). | ________ | ________ |
| (f) | ________ | ________ |
| (g) Subtotal | ________ | ________ |
| (h) General Contractor’s Overhead and Profit: Not to exceed fifteen percent (15%) of Item (g) if Contractor performed the work. No more than five percent (5%) of Item (g) if Subcontractor performed the work. If work was performed by Contractor and Subcontractors, portions performed by Contractor shall not exceed fifteen percent (15%) if Item (g), and portions performed by Subcontractor shall not exceed five percent (5%) of Item (g) | ________ | ________ |
| (i) Subtotal | ________ | ________ |
| (j) Bond not to exceed one percent (1%) of Item (g) | ________ | ________ |
| (k) TOTAL | ________ | ________ |
| (l) Time | ________ | ________ |

The undersigned Contractor approves the foregoing Change Order or Construction Change Directive as to the changes, if any, and the contract price specified for each item and as to the extension of time allowed, if any, for completion of the entire work on account of said Change Order or Construction Change Directive, and agrees to furnish all labor, materials and service and perform all work necessary to complete any additional work specified therein, for the consideration stated herein.  It is understood that said Change Order or Construction Change Directive shall be effective when approved by the Governing Board of the District.

It is expressly understood that the value of such extra Work or changes, as determined by any of the aforementioned methods, expressly includes any and all of the Contractor’s costs and expenses, both direct and indirect, resulting from additional time required on the Project or resulting from delay to the Project.  Any costs, expenses, damages or time extensions not included are deemed waived.

The Contractor expressly acknowledges and agrees that any change in the Work performed shall not be deemed to constitute a delay or other basis for claiming additional compensation based on theories including, but not limited to, acceleration, suspension or disruption to the Project.

  - Failure to Agree as to Cost for Added Work.  Notwithstanding the failure of the District and the Contractor to agree as to the cost of the proposed change order, the Contractor, upon written order from the District, shall proceed immediate with the changed Work.  A field instruction or letter signed by the District shall be used for this written order.  At the start of each day’s work on the change, the Contractor shall notify the District in writing as to the size of the labor force to be used for the changed work and its location.  Failure to notify may result in the non-acceptance of the costs for that day.  At the completion of each day’s work, the Contractor shall furnish to the Inspector a detailed summary of all labor, materials, and equipment employed in the changed Work.  The Inspector will compare his or her records with the Contractor’s daily summary and may make any necessary adjustments to the summary.  After the Inspector and the Contractor agree upon and sign the daily summary, the summary shall become the basis for determining costs for the additional Work.  The sum of these costs when added to the appropriate mark-up will constitute the payment for the changed Work.  Subsequent adjustments, however, may be made based on later audits by the District.  When changed Work is performed at locations away from the job site, the Contractor shall furnish in lieu of the daily summary, a summary submitted at the completion of the Work containing a detailed statement of labor, material, and equipment used in the Work.  This latter summary shall be signed by the Contractor who shall certify thereon that the information is true.  The Contractor shall maintain on demand and furnish on demand of the District itemized statements of cost from all vendors and subcontractors who perform changed work or furnish materials and equipment for such Work.  All statements must be signed by the vendors and the subcontractors.

  - Failure to Agree as to Cost for Deleted Work,  When a proposed change order contains a deletion of any work, and the District and the Contractor are unable to agree upon the cost thereon, the District’s estimate shall be deducted from the Contract Price and may be withheld from the payment due to the Contractor until the Contractor presents proof convincing to the District that District’s estimate was in error.  The amount to be deducted shall be the costs to the Contractor for labor, materials, and equipment which would have been used on the deleted work together with the amount for overhead and bonds.  The guidelines set forth in Section 16.3 above shall be used in computing the amounts involved.

  - Allowable Time Extensions.  For any change in the Work, the Contractor shall be entitled only to such adjustments in time by which completion of the entire Work is delayed due solely to performance of the changed Work.  However, no extension of time shall be granted for a change in the Work unless the Contractor demonstrates to the satisfaction of the District that (a) the Work is on the critical path as shown on an updated Construction Schedule showing that an extension of time is required, and (b) the Contractor is making, or has made, every reasonable effort to guarantee completion of the additional Work called for by the change within the time originally allotted for the Work.  Any such time adjustment shall be on a calendar day basis, except that if the new Contractual Completion Date falls on a Saturday, Sunday, or legal holiday, it shall be extended through the next working day.

Construction Manager May Authorize Minor Variations in Limited Situations.  The Construction manager may authorize minor variations in the Work, but only if those minor variations (a) do not affect the Contract Price, (b) do not affect the Construction Schedule, (c) do not violate Applicable Laws, and (d) are consistent with the overall intent of the Plans, Specifications and other Project Documents.

CONSTRUCTION CHANGE DIRECTIVE NO.

PROJECT: ________________________________________________________________

TO: ________________________________________________________________

You are hereby directed to provide the extra work necessary to comply with this Construction Change Directive.

DESCRIPTION OF CHANGE: ________________________________________________________________

________________________________________________________________

NOTE:

Contractor agrees to furnish all labor and materials and perform all of the above-described work in accordance with the above terms in compliance with the applicable sections of the Contract documents.  The amount of the charges under this Construction Change Directive is limited to the charges allowed under Article 7 of the General Conditions.  The adjustment in the contract sum, if any, and the adjustment in the contract time, if any, set out in this Construction Change Directive shall constitute the entire compensation and/or adjustment in the contract time and contract sum due to the Contractor arising out of the change in the work covered by this Construction Change Directive, unless otherwise provided in this Construction Change Directive.

CHANGE ORDER NO.

PROJECT:_______________________________________________________

TO:_____________________________________________________________

You are hereby directed to provide the extra work necessary to comply with this Change Order.

DESCRIPTION OF CHANGE:________________________________________

________________________________________________________________

COST (This cost shall not be exceeded): _______________________________

Original Contract Price:		 $_______________________

Change Order Amount:		 $_______________________

New Contract Price:			 $________________________

TIME FOR COMPLETION: _______________________________________

Original Completion Date:________________________________

Time for Completion of CO:________________________________

New Completion Date: ___________________________________

NOTE:

Contractor agrees to furnish all labor and materials and perform all of the above-described work in accordance with the above terms in compliance with the applicable sections of the Contract documents.  The amount of the charges under this Change Order is limited to the charges allowed under Article 7 of the General Conditions.  The adjustment in the contract sum, if any, and the adjustment in the contract time, if any, set out in this Change Order shall constitute the entire compensation and/or adjustment in the contract time and contract sum due to the Contractor arising out of the change in the work covered by this Change Order, unless otherwise provided in this Change Order.  It is understood that this Change Order shall be effective when approved by the Governing Board of the District.

- BONDS

The Contractor shall furnish a Payment Bond in an amount equal to one hundred percent (100%) of Contract Price as security for payment to persons performing labor and furnishing materials in connection with this Project, and shall furnish a separate Faithful Performance Bond in an amount equal to one hundred percent (100%) of the Contract Price as security for faithful performance of the Agreement.  Those bonds shall be in the forms included among the Project Documents.

- INSURANCE

  - Inapplicability of This Article if Project is Subject to OCIP.  If the Notice Calling for Bids indicates that the District has elected to include this Project in the OCIP, then this Article shall apply only to the extent that the insurance required herein is not provided by the District through the OCIP.  In that case, the Contractor shall refer to the OCIP Addendum identified in the Information for Bidders to determine the extent to which the provisions of this Article 18 shall apply to the Project.

  - Fire Insurance.  The Contractor will procure at the Contractor’s own expense, and before commencement of any Work under the Agreement, fire insurance on the Project with course of construction, without exclusions, vandalism, and malicious mischief clauses attached.  The amount of fire insurance shall be the greater of (a) an amount sufficient to protect against loss or damage in full until the Work is accepted by the District or (b) the amount specified in the Agreement.  The Contractor shall submit proof of insurance and shall provide endorsements on forms provided by the District or on forms approved by the District.  Such endorsements shall be submitted concurrently with the Contractor’s execution of the Agreement.

  - Commercial General Liability and Property Damage Insurance.  The Contractor shall procure and maintain during the life of the Agreement such commercial general liability and property damage insurance as shall protect the Contractor and the District from all claims for personal injury, including accidental death, to any person (including, as to the District, injury or death to the Contractor’s or subcontractor’s employees), as well as from all claims for property damage arising from operations under the Agreement, in amounts as set forth in the Agreement.  The amount of such insurance shall be as specified in the Agreement.  The Contractor shall require its Subcontractors to procure and maintain similar commercial general liability and property damage insurance in like amounts, or in such other amounts specified in the Agreement.  The Contractor shall submit to the District (through the Construction Manager) proof of insurance and shall provide endorsements on the forms provided by (or approved by) the District.  Such endorsements shall be submitted concurrently with the Contractors’ execution of the Agreement.

  - Workers’ Compensation Insurance.  In accordance with the provisions of Section 3700 of the California Labor Code, the Contractor and every Subcontractor shall be required to secure the payment of compensation to its employees.  In that regard, the Contractor shall provide, during the life of the Agreement, workers’ compensation insurance for all of its employees engaged in Work under the Agreement, on or at the site of the Project, and, in case any of its Work is sublet, the Contractor shall require each Subcontractor similarly to provide workers’ compensation insurance for all of that Subcontractor’s employees.  Any class of employee or employees not covered by a subcontractor’s insurance shall be covered by the Contractor’s insurance.  In case any class of employees engaged in Work under the Agreement, on or at the site of the Project, is not protected under applicable workers’ compensation statutes, the Contractor shall provide (or, where appropriate, shall cause its Subcontractors to provide) adequate insurance coverage for the protection of such employees not otherwise protected before the Contractor or Subcontractor commences work.  The Contractor shall file with the District certificates of its insurance protecting workers and a thirty (30) day notice shall be provided to the District before the cancellation or reduction of any policy of the Contractor or Subcontractor.  The Contractor shall submit proof of insurance and shall provide endorsements on the forms provided by the District or on forms approved by the District.  Such endorsements shall be submitted concurrently with the Project Documents.

  - Proof of Insurance.  The Contractor shall not commence work, nor shall it allow any subcontractor to commence work, under the Agreement or relative to the Project until all insurance certificates and endorsements required by this Article 18 have been obtained and delivered to the Construction Manager for approval by the District and the District has approved same.  Each policy of insurance required by this Article 18 shall be with an insurance company with a minimum rating of “A/VIII”, as rated by the current edition of the Best’’ Key Rating Guide/Property-Casualty, published by A.M. Best Co., Oldwick, New Jersey 08858 and must be admitted carriers in California (no surplus lines or other non-admitted carriers otherwise permitted to do business in California will be accepted).  Certificates and insurance policies shall include the following:

    - A clause stating: “This policy shall not be canceled or reduced in required limits of liability or amount of insurance until notice has been mailed to the Moreno Valley Unified School District stating date of cancellation or reduction.  Date of cancellation or reduction may not be less than thirty (30) days after date of mailing notice.”

    - Language stating in particular the names of the insured parties, the extent of the insurance, the location and Project to which the insurance applies, the expiration date, the name and address of the District representative to whom cancellation and reduction notices will be sent, and the length of any notice period.

    - A statement that the District, the Architect and the Construction Manager are each a named additional insured under the policy described and that such insurance policy shall be primary to any insurance or self-insurance maintained by the District.

  - District May Obtain Insurance at Contractor’s Expense.  If the Contractor fails to provide insurance as required by the Agreement, the District may, at the District’s option, procure and maintain such insurance as the District may deem proper, at the Contractor’s expense, in the name of the Contractor (or Subcontractor, as applicable), and may deduct the cost thereof from any sums which are due or to become due to the Contractor under the Agreement.

CLAIMS AND DAMAGES

  - Decision of Architect.  Disputes between District and Contractor involving money or time, including those alleging an error or omission by the Architect, shall be referred initially to the Architect for action as provided in Paragraph 4.5.2.  A decision by the Architect, as provided in Paragraph 4.5.5, shall be required as a condition precedent to proceeding with remedies set forth in Paragraph 4.5.6 as to all such matters arising prior to the date final payment is due, regardless of whether such matters relate to execution and progress of the Work, or the extent to which the Work has been completed.  The decision by the Architect in response to a Claim shall not be a condition precedent to the remedies under Paragraph 4.5.2 through 4.5.5  in the event: (1) the position of Architect is vacant; (2) the Architect has not received evidence or has failed to render a decision within agreed time limit; (3) the Architect has failed to take action required under Paragraph 4.6.4 within thirty (30) days after the Claim is made, forty-five (45) days have passed after the Claim has been referred to the Architect; or (4) the Claim relates to a Stop Notice Claim not arising from any extra change order or Construction Change Directive for which approval has not been provided.

  - Architect’s Review.  The Architect will review claims and take one or more of the following preliminary actions within ten (10) days of receipt of a claim: (1) request additional supporting data from the claimant; (2) submit a schedule to the parties indicating when the Architect expects to take action; (3) reject the claim in whole or in part, stating reasons for rejection; (4) recommend approval of the claim; or (5) suggest a compromise.  The Architect may also, but is not obligated to, notify the surety, if any, of the nature and amount of the claim.

  - Documentation if Resolved.  If a claim has been resolved, the Architect will prepare or obtain appropriate documentation.

  - Actions if Not Resolved.  If a claim has not been resolved and all documentation requested pursuant to Paragraph 4.5.2 has been provided, the party making the claim shall, within ten (10) days after the Architect’s preliminary response, take one or more of the following actions: (1) modify the initial claim; (2) notify the Architect that the initial claim stands; or (3) supplement with additional supporting data.

  - Architect’s Written Decision.  If a claim has not been resolved after consideration of the foregoing and of other evidence presented by the parties or requested by the Architect, the Architect will notify the parties in writing that the Architect’s decision will be made within twenty (20) days.  Upon expiration of such time period, the Architect will render to the parties its written decision relative to the claim, including any change in the Contract Sum or Contract Time or both.  The Architect may, but is not obligated to, notify the surety and request the surety’s assistance in resolving the controversy.

  - Continuing Contract Performance.  Pending final resolution of a Claim, including, negotiation, mediation, arbitration, or litigation, the Contractor shall proceed diligently with performance of the Contract, and the District shall continue to make any undisputed payments in accordance with the Contract.  If the dispute is not resolved, Contractor agrees it will neither rescind the contract nor stop the progress of the work, but Contractor’s sole remedy shall be to submit such controversy to determination by a court of competent jurisdiction in the county where the project is located, after the project has been completed, and not before.  At the District’s sole option, the District may submit individual disputes for binding arbitration and Contractor agrees to the resolution determined for each individual dispute by Arbitrator, including resolution of time and delays.  If binding arbitration is utilized for individual disputes, such resolution is full and final as to that particular claim.

  - Claims for Concealed Trenches or Excavations Greater Than Four Feet Below the Surface.  When any excavation or trenching extends greater than four feet below the surface or if any condition involving hazardous substances are encountered:

###### (a)	Immediately upon discovery, The Contractor shall promptly, and before the following conditions are disturbed, notify the public entity, by telephone and in writing, of the condition except:

- 1.	If such condition is a hazardous waste condition, Contractor’s bid includes removal or disposal of hazardous substances.  Material that the Contractor believes may be a material that is hazardous waste, as defined in Section 25117 of the Health and Safety Code that is required to be removed to a Class I, Class II, or Class III disposal site in accordance with the provisions of existing law.  In such case, the notice bulletin procedures of Article 7 apply.

- 2.	Subsurface or latent physical conditions at the Site differing from those indicated.

- 3.	Unknown physical conditions at the Site of any unusual nature, different materially from those ordinarily encountered and generally recognized as inherent in Work of the character provided for in the Contract.

###### (b)	The public entity shall investigate the conditions, and if District finds that the conditions do materially so differ, do involve hazardous waste, and cause a decrease or increase in the Contractor’s cost of, or the time required for, performance of any part of the Work shall issue a change order or construction change directive under the procedures described in the Contract.

###### (c)	In the event that a dispute arises between the public entity or District and the Contractor whether the conditions materially differ, involve hazardous waste, or cause a decrease or increase in the Contractor’s cost of, or time required for, performance of any part of the work, the Contractor shall not be excused from any scheduled completion date provided for by the Contract, but shall proceed with all Work to be performed under the Contract.  The Contractor shall retain any and all rights provided either by Contract or by law which pertain to the resolution of disputes and protests between the contracting parties.

  - Claims for Extension of Time.  If Contractor and District cannot agree upon an extension of time, whether compensable or not, then Contractor must have first completed the procedures set forth in Paragraph 8.4.  Upon completion of the procedures set forth under Paragraph 8.4, Contractor must then comply with the requirements in this Article including those set forth under Paragraph 4.5.9.

  - Claims Procedures.  Procedure applicable to all Claims:

###### (a)	Definition of Claim:  A “Claim” means a separate demand by the Contractor for (1) time extension, (2) payment of money or damages arising from Work done by or on behalf of the Contractor pursuant to the CONTRACT and payment of which is not otherwise expressly provided for or the claimant is not otherwise entitled to, or (3) and amount the payment of which is disputed by the District.

###### (b)	Filing Claim is Not Basis To Discontinue Work:  The Contractor shall promptly comply with Work under the Contract or Work requested by the District even though a written claim has been filed.  The Contractor and the District shall make good faith efforts to resolve any and all claims that may arise during the performance of the Work covered by this contract.

###### (c)	Claim Notification:  The Contractor shall within seven (7) calendar days after the claim arises, submit a notification, in writing, with the District stating clearly the basis for the claim.  If the notification is not submitted within seven (7) days after the claim arises, the Contractor shall be deemed to have waived all right to assert the claim, and the claim shall be denied.  Claims submitted after the final payment date shall also be considered null and void by the District.  All claims shall be reviewed pursuant to Paragraph 4.5.1, 4.5.2, and 4.5.5.

###### (d)	Formal Claim Submission:  If the Contractor does not concur with the District’s decision regarding the Claim Notification, the Contractor will issue a formal Claim Appeal within fourteen (14) days of receipt of the District’s decision and all detailed information in support of the Claim Appeal within thirty (30) days.  All appeals shall be submitted before final payment.  If the Claim Appeal is not submitted within fourteen (14) calendar days and detailed information within thirty (30) days, the Contractor shall be deemed to have waived its right to assert the Claim and the Claim shall be denied.  Contractor’s failure to submit any detailed information which is in the possession of Contractor shall render such information inadmissible by Contractor at trial or arbitration.

###### (e)	Appeal Claim Format:  The Contractor shall provide all written detailed documentation which supports the claim, including but not limited to:  arguments, justifications, cost, estimates, schedule analysis and detailed documentation.  The format of the Claim Appeal shall be as follows:

- Cover letter.

- Summary of factual basis of claim and amount of claim.

- Summary of the basis of the claim, including the specific clause and section under the Contract under which the claim is made.

- Documents relating to the claim, including:

- Specifications

- Drawings

- Clarifications (RFI’s)

- Other relevant information

- Analysis of claim merit

- Analysis of claim cost

- For claims relating to time extensions, an analysis and supporting documentation evidencing any effect upon the critical path

- Certification

- Chronology of events and related correspondence

- Daily reports and logs

###### (f)	Certification:  The Contractor (and subcontractors, if applicable) shall submit with the claim a certification under penalty of perjury:

- That the Contractor has reviewed the claim and that such claim is made in good faith;

- Supporting data are accurate and complete to the best of the Contractor’s knowledge and belief;

- The amount requested accurately reflects the amount of compensation for which the Contractor believes the District is liable.

- That the Contractor is familiar with Government Code Sections 12650 et seq. and Penal Code Section 72 and that false claims can lead to substantial fines and/or imprisonment.

###### (g)	Signature of Certification:  If the Contractor is not an individual, the certification shall be executed by an officer or general partner of the Contractor having overall responsibility for the conduct of the Contractor’s affairs.

###### (h)	Mandatory Claim Appeal Procedure:  The Contractor’s Claim Appeal shall be denied if it fails to provide the written basis of the claim and certification as set forth herein.

###### (i)	District May Request Additional Information:  Within thirty (30) days of receipt of the Claim Appeal and the information under this Article, the District may request in writing any additional documentation supporting the claim or documentation relating to defenses to the claim which the District may assert.

  - Binding Arbitration of Individual Claim Issues.  At the District’s sole option, the District may submit individual disputes, or claims, to binding arbitration and Contractor agrees to the resolution determined for each individual dispute by Arbitrator, including resolution of time and delays.  If binding arbitration is utilized, such resolution is a full and final resolution of the particular claim or dispute.  Under no circumstances may the Contractor stop work, rescind its contract or otherwise slow the progress of Work during resolution of individual claims in binding Arbitration.

  - Resolution of Disputes in Court of Competent Jurisdiction.  If claims are not resolved under the procedure set forth and pursuant to Article 4.5.9.2, such claim or controversy shall be submitted to a court in the county of competent jurisdiction after the Project has been completed, and not before.

  - Warranties, Guarantees and Obligations.  The duties and obligations imposed by these General Conditions and the rights and remedies available hereunder to the parties hereto, and, in particular but without limitation, the warranties, guarantees and obligations imposed upon Contractor by the General Conditions and amendments thereto; and all of the rights and remedies available to District and Architect there under, are in addition to, and are not to be construed in any way as a limitation of, any rights and remedies available to any or all of them which are otherwise imposed or available by laws or regulations by special warranty or guarantee or by other provisions of the Contract Documents, and the provisions of this Paragraph will be as effective as if repeated specifically in the Contract Documents in connection with each particular duty, obligation, right and remedy to which they apply.

- WARRANTY OF WORK

  - Warranty as to Condition of Work.  The Contractor warrants that the Work (including without limitation any equipment furnished by the Contractor as part of the materials) shall: (a) be free from defects in workmanship and material; (b) be free from defects in any design performed by the Contractor; (c) be new, (d) conform and perform to the requirements stated in the specifications or, where detail requirements are not so stated, shall conform to applicable industry standards; and (e) be suitable for the use stated in the specifications.

  - Warranty Period.  The warranty period for discovery of defective work shall commence on the date stamped on the Notice of Completion verifying County recordation and continue for the period set forth in the specifications or for one year if not so specified.  If, during the warranty period, the Work is not available for use due to defective work, such time of unavailability shall not be counted as part of the warranty period.  The warranty period for corrected defective work shall continue for a duration equivalent to the original warranty period.

  - Correction of Defective Work.  The District shall give the Contractor prompt written notice after discovery of any defective Work.  The Contractor shall correct any such defective Work, as well as any damage to any other part of the work resulting from such defective Work, and provide repair, replacement, or reimbursement, at its sole expense, in a manner approved by the District and with due diligence and dispatch as required to make the Work ready for use by the District, ordinary wear and tear and unusual abuse or neglect excepted.  Such corrections shall include, but not be limited to, any necessary adjustments, modifications, changes of design, removal, repair, replacement or reinstallation, and shall include all necessary parts, materials, tools, equipment, transportation charges and labor as may be necessary, and cost of removal and replacement of Work shall be performed at a time and in such a manner so as to minimize the disruption to District’s use of the Work.

  - District’s Right to Correct Defects.  In the event of failure of the Contractor or Surety to commence and pursue with diligence said repairs or replacements within seven (7) days after being notified in writing, the District is hereby authorized to proceed to have defects repaired or replaced and made good at expense of the Contractor and Surety who hereby agree to pay costs and charges therefore immediately on demand.

  - Limitation on Notice Requirements.  If, in the opinion of the District, defective Work creates a dangerous condition or requires immediate correction or attention to prevent further loss to the District or to prevent interruption of operations of the District, the District will attempt to give the written notice required by this Article 20.  If the Contractor or its surety cannot be contacted, or if neither the Contractor or its surety complies with the District’s requirements for correction within a reasonable time as determined by the District, the District may, notwithstanding the provisions of this Article, proceed to make such correction or provide such attention and the costs of such correction or attention shall be charged against the Contractor and its surety.  Such action by the District will not relieve the Contractor and its surety of the warranties and guarantees provided in this Article 20 or elsewhere in the Project Documents.

  - No Effect on Other Guarantees.  This Article does not in any way limit the guarantees on any items for which a longer guarantee is specified or on any items for which a manufacturer gives a guarantee for a longer period.  The Contractor shall furnish to the District all appropriate guarantee or warranty certificates upon completion of the Project or upon request by the District.

  - Form of Guaranty.  If required by the District, all guarantees required under this Article 20 shall be in writing on a guarantee form prepared by the District.

  - Instruction Manuals.  The Contractor shall provide to the District instruction manuals for all warrantied items which require same.

  - No Limitation on District’s Other Rights.  Nothing herein shall limit any other rights or remedies available to the District.

  - Attorneys’ Fees.  Each party shall bear their own attorney's fees and costs in any action to enforce this article. The District may collect its reasonable costs and attorneys’ fees in any action to enforce this Article.

- PAYMENTS TO CONTRACTOR

  - Cost Breakdown and Periodic Estimates.  The Contractor shall furnish the following, at the times specified, on forms approved by the District:

    - Within three (3) calendar days after the District’s award to the Contractor of the contract for the Project, a detailed estimate giving complete breakdown of the Contract Price for the Project (and each site thereof, where the Project involves multiple sites), which shall include all subcontracts and supplier agreements, showing dollar amounts of these agreements to justify the subsequently-provided schedule of values;

    - Monthly itemized estimate of work done for purpose of making partial payments thereon; and

    - Within five (5) calendar days of request of the District, a schedule of estimated monthly payments which shall be due the Contractor under the Agreement.

Values employed in making up any of these schedules are subject to the Architect’s written approval and will be used only for determining basis of partial payments and will not be considered as fixing a basis for additions to or deductions from contract price.

  - Monthly Payments by the District to the Contractor.  Unless otherwise specified in writing, each month within thirty (30) days after receipt by the District of the monthly progress schedule and the certification of application for payment by the Architect, the District shall pay to the Contractor a sum equal to ninety percent (90%) of value of work performed and of materials delivered subject to or under the control of the District and unused up to the last day of the previous month, less aggregate previous payments.  Monthly payments shall be made only on the basis of monthly estimates which shall be prepared by the Contractor on a form approved by the District and filed before the fifth (5th) day of the month during which payment is to be made.  Work completed as estimated shall be an estimate only and no inaccuracy or error in said estimate shall operate to release the Contractor or its surety from any damages arising from such Work or from enforcing each and every provision of the Agreement, and the District shall have the right subsequently to correct any error made in any estimate for payment.  THE CONTRACTOR SHALL NOT BE ENTITLED TO HAVE ANY PAYMENT ESTIMATES PROCESSED OR BE ENTITLED TO HAVE ANY PAYMENT FOR WORK PERFORMED SO LONG AS ANY LAWFUL OR PROPER DIRECTION CONCERNING WORK, OR ANY PORTION THEREOF, GIVEN BY THE DISTRICT, THE CONSTRUCTION MANAGER OR THE ARCHITECT SHALL REMAIN UNCOMPLIED WITH BY THE CONTRACTOR.

  - Schedule of Values.  To assist in computing partial payments, the Contractor shall submit to the Architect, the Construction Inspector, and the District a “Schedule of Values” of the Contractor’s actual and estimated cost for each item of Work.  The cost breakdowns shall be sufficient detail for use in estimating the Work to be completed each month and shall be submitted within twenty (20) days after the date of the Notice to Proceed.

  - Monthly Payment Requests.  Once each month during the progress of the Work, the Contractor shall submit to the Architect a partial payment request which has been received and agreed to by the Architect and the District’s Inspector (as well as by the Construction Manager, if one has been appointed by the District for the Project).  The partial payment request shall be based on the approved bid breakdown for the cost of the Work completed plus the acceptable materials delivered to the site or stored subject to the control of the Contractor and not yet installed.  The partial payment request shall be submitted on the monthly anniversary of the day selected by the Contractor in the job starting meeting.

  - Partial Payments; Retention.  The Architect and Construction Inspector shall review and certify as to the validity of the requests.  No partial payment shall be made without the certification of the Architect.  Partial payment requests shall be processed within a minimum of a ten percent (10%) retention.  The retention is part of the security for the fulfillment of the Agreement by the Contractor.  Partial payment shall not be construed as acceptance of any work which is not in accordance with requirements of the Agreement.  Once the partial payment request has been certified by the Architect and the Construction Inspector, it shall be submitted to the District’ Construction Manager for approval and processing.  Such procedures provided for sixty (60) days processing, from the date the receipt at the District Office by the Construction Manager, prior to late payment penalty.

  - Information Required from Contractor.  The District has discretion to require from the Contractor any of the following information with the application for payment: (a) certified payroll covering the period of the prior application for payment; (b) unconditional waivers and releases from all subcontractors and suppliers for which payment was requested under the prior application for payment; (c) receipts or bills of sale for any items.

  - Contractor’s Certificate.  Before payment is made hereunder, a certificate in writing shall be obtained from the Architect stating that the Work for which the payment is demanded has been performed in accordance with the terms of the Project Documents and that the amount stated in the certificate is due under the terms of the Project Documents, which certificate shall be attached to and made a part of the claim made and filed with the District, provided that if the Architect shall, within three (3) days after written demand therefore, fail to deliver such certificate to the District, the Contractor may file its claim with the District without said certificate, but together with such claim shall be filed a statement that demand was made for such certificate and that the same was refused.  Thereupon, the District will either allow said claim as presented or shall, by an order entered on the minutes of said the District state the reasons for refusing to allow said claim.  It is understood, moreover, that the certificate of the Architect shall not be conclusive upon the District, but advisory only.

    - Payment Does Not Constitute Acceptance of Work.  NO PAYMENT BY THE DISTRICT HEREUNDER SHALL BE INTERPRETED SO AS TO IMPLY THAT THE DISTRICT HAS INSPECTED, APPROVED, OR ACCEPTED ANY PART OF THE WORK.  The final payment of the ten percent (10%) retention of the value of the Work done under the Agreement, if unencumbered, shall be made thirty-five (35) days after recording by the District of the Notice of Completion.  ACCEPTANCE WILL BE MADE ONLY BY ACTION OF THE DISTRICT’S SCHOOL BOARD pursuant to Section 8.3 above.

  - Final Payment.  Unless otherwise provided, on or before making request for final payment of the undisputed amount due under the Agreement, the Contractor shall submit to the District, in writing, a summary of all claims for compensation under or arising out of the Agreement which were timely filed.  The acceptance by the Contractor of the payment of the final amount shall constitute a waiver of all claims against the District under or arising out of the Agreement, except those previously made, in a timely manner and in writing, and identified by the Contractor as unsettled at the time of the Contractor’s final request for payment.

  - Adjustments to Contract Price.  If the Contractor defaults or neglects to carry out the Work in accordance with the Project Documents or fails to perform any provision thereof, the District may, after seven (7) days written notice to the Contractor and without prejudice to any other remedy it may have, make good such deficiencies.  The District shall adjust the total Contract Price by reducing the amount thereof by the cost of making good such deficiencies.  If the District deems it inexpedient to correct Work not done in accordance with the Project Documents, an equitable reduction in the Contract Price shall be made therefore.

  - Payments Withheld in Addition to Retention Amounts.  In addition to any other amounts which the District may retain under this Article 21, the District may withhold a sufficient amount or amounts of any payment or payments otherwise due to the Contractor, as in its judgment may be necessary to cover:

    - Payments which may be past due and payable for claims against the Contractor or any Subcontractors, or against and about the performance of Work on the Project, including, without limitation, payments made pursuant to Section 7.16 above.

    - The value determined by the District to be attributable to delayed delivery of the initial Construction Schedule beyond the time required under Article 5.

    - The value determined by the District attributable to the Contractor’s failure to provide updated as-built drawings for the Inspector’s review.

    - The cost of defective Work which the Contractor has not remedied.

    - Claims made pursuant to the stop notice provisions of Civil Code Sections 9100 et seq.

    - Liquidated damages assessed against the Contractor.

    - Penalties for violation of labor laws.

    - The cost of materials ordered by the District for the Project to the extent authorized under these General Conditions or the other Project Documents.

    - The cost of completion of the Work if there exists a reasonable doubt that the Work can be completed for the balance then unpaid to the Contractor.

    - Damage to another contractor.

    - Site clean-up as provided in Section 7.15 above.

    - Payments to indemnify, defend, or hold harmless the District.

    - Any payments due to the District including but not limited to payments for failed tests, utilities or imperfections.

    - Extra services for the Architect, including without limitation additional back-check to sign off punch-list items.

    - Extra services for the Inspector and/or Construction Manager, including without limitation (a) re-inspection required due to the Contractor’s failed tests or installation of unapproved or defective materials and (b) the Contractor’s requests for inspection and the Contractor’s subsequent failure to attend that inspection.

    - Failure to complete a punch list with diligence.

If the above grounds are in the opinion of the District removed by or at the expense of the Contractor, payment shall be made for amounts withheld because of them.  The District may apply such withheld amount or amounts to payment of such claims or obligations at its discretion.  In so doing, the District shall make such payments on behalf of the Contractor.  If any payment is so made by the District, then such amount shall be considered as a payment made under contract by the District to the Contractor and the District shall not be liable to the Contractor for such payments made in good faith.  Such payments may be made without prior judicial determination of claim or obligations.  The District will render the Contractor an accounting of such funds disbursed on behalf of the Contractor.  As an alternative to payment of such claims or obligations, the District, in its sole discretion, may reduce the total Contract Price as provided in Section 21.9 above.

  - Reimbursable Expenses.  Any payments to third parties made by the Contractor on the District’s behalf in connection with the Project, whether or not specifically characterized in any of the Project Documents as being “reimbursable” (but excluding payments for items that are specifically identified in any of the Project Documents as payable by the Contractor at the Contractor’s expense), shall be calculated as direct reimbursable expenses and shall not be included in the Contractor’s base bid; as such, the amount of reimbursement owing by the District to the Contractor shall be limited to the actual payment made by the Contractor to the third party, and shall not include any mark-up, premium or other additional amount for the Contractor’s profit, overhead or other expenses.  The Contractor shall submit requests for reimbursement of such payments as part of the Contractor’s monthly payment requests pursuant to Section 21.4 above, and payment by the District shall be made pursuant to Sections 21.5 through 21.10 above.

- DISTRICT’S RIGHT TO TERMINATE AGREEMENT

# TERMINATION OR SUSPENSION OF THE CONTRACT

## 22.1	Termination By The Contractor For Cause.  Grounds for Termination.  The Contractor may terminate the Contract if the Work is stopped for a period of thirty (30) consecutive days through no act or fault of the Contractor, a Subcontractor, a Sub-subcontractor, their agents or employees, or any other persons performing portions of the Work for whom the Contractor is contractually responsible, for only the following reasons:

##### (a)	Issuance of an order of a court or other public authority having jurisdiction; or

##### (b)	An act of government, such as a declaration of national emergency.

If one of the above reasons exists, the Contractor may, upon written notice of seven (7) additional days to the District, terminate the Contract and recover from the District payment for Work executed and for costs that are actual, reasonable, and verified by the Architect with respect to materials, equipment, tools, construction equipment, and machinery, including reasonable overhead, profit, and damages.

## 22.2	Termination By The District For Cause.  Grounds for Termination.  The District may terminate the Contractor and/or this Contract for the following reasons:

##### (a)	Persistently or repeatedly refuses or fails to supply enough properly skilled workers or proper materials;

##### (b)	Persistently or repeatedly is absent, without excuse, from the job site;

##### (c)	Fails to make payment to Subcontractors, suppliers, material men, etc.;

##### (d)	Persistently disregards laws, ordinances, rules, regulations, or orders of a public authority having jurisdiction; or

##### (e)	Otherwise is in substantial breach of a provision of the Contract Documents.

22.3	Notification of Termination.  When any of the above reasons exist, the District may, without prejudice to any other rights or remedies of the District and after giving the Contractor and the Contractor’s surety, if any, written notice of seven (7) days, terminate the Contractor and/or this Contract and may, subject to any prior rights of the surety:

##### (a)	Take possession of the Project and of all material, equipment, tools, and construction equipment and machinery thereon owned by the Contractor;

##### (b)	Accept assignment of Subcontracts. Contractor acknowledges and agrees that if the District (in its sole and absolute discretion) decides to takeover completion of the Project, the Contractor agrees to immediately assign all subcontracts to the District which the District has chosen to accept; and

##### (c)	Complete the Work by any reasonable method the District may deem expedient, including contracting with a replacement contractor or contractors.

##### 22.4	Payments Withheld.  If the District terminates the Contract for one of the reasons stated in Paragraph 22.2, the Contractor shall not be entitled to receive further payment until the Work is complete. All costs associated with the termination and completion of the Project shall be the responsibility of the Contractor and/or its surety.

### 22.5	Payments Upon Completion.  If the unpaid balance of the Contract Sum exceeds costs of completing the Work, including compensation for professional services and expenses made necessary thereby, such excess shall be paid to the Contractor.  If such costs exceed the unpaid balance, the Contractor shall pay the difference to the District.  The amount to be paid to the Contractor, or District, as the case may be, shall be certified by the Architect upon application.  This payment obligation shall survive completion of the Contract.

## 22.6	Termination Of Contract By District (Contractor Not At Fault).  Termination for Convenience.  District may terminate the Contract upon fifteen (15) calendar days of written notice to the Contractor and use any reasonable method the District deems expedient to complete the project, including contracting with replacement contractor or contractors, if it is found that reasons beyond the control of either the District or Contractor make it impossible or against the District’s interest to complete the work.  In such a case, the Contractor shall have no claims against the District except: (1) the actual cost for labor, materials, and services performed which may be documented through timesheets, invoices, receipts, or otherwise and which has not already been paid by the District, and (2) ten percent (10%) profit and overhead of item (1), and (3) five percent (5%) termination cost of the total of items (1) and (2). Contractor acknowledges and agrees that if the District (in its sole and absolute discretion) decides to takeover completion of the Project, the Contractor agrees to immediately assign all subcontracts to the District which the District has chosen to accept.

### 22.7	Non-Appropriation of Funds/ Insufficient Funds.  In the event that sufficient funds are not appropriated to complete the Project or the DISTRICT determines that sufficient funds are not available to complete the Project, DISTRICT may terminate or suspend the completion of the Project at any time by giving written notice to the Contractor.  In the event that the DISTRICT exercises this option, the DISTRICT shall pay for any and all work and materials completed or delivered onto the site for which value is received, and the value of any and all work then in progress and orders actually placed which cannot be canceled up to the date of notice of termination.  The value of work and materials paid for shall include a factor of fifteen percent (15%) for the Contractor’s overhead and profit and there shall be no other costs or expenses paid to Contractor.  All work, materials and orders paid for pursuant to this provision shall become the property of the DISTRICT. DISTRICT may, without cause, order Contractor in writing to suspend, delay or interrupt the Project in whole or in part for such period of time as DISTRICT may determine.  Adjustment shall be made for increases in the cost of performance of the Agreement caused by suspense, delay or interruption.

## 22.8	Remedies Other Than Termination.  If a default occurs, the District may, without prejudice to any other right or remedy, including, without limitation, its right to terminate the Contract pursuant to Article 14.2, do any of the following:

###### (a)	Permit the Contractor to continue under this Contract, but make good such deficiencies or complete the Contract by whatever method the District may deem expedient, and the cost and expense thereof shall be deducted from the Contract Price or paid by the Contractor to the District on demand;

###### (b)	If the workmanship performed by the Contractor is faulty or defective materials are provided, erected or installed, then the District may order the Contractor to remove the faulty workmanship or defective materials and to replace the same with work or materials that conform to the Contract Documents, in which event the Contractor, at its sole costs and expense, shall proceed in accordance with the District’s order and complete the same within the time period given by the District in its notice to the Contractor; or

###### (c)	Initiate procedures to declare the Contractor a non-responsible bidder for a period of two to five years thereafter.

All amounts expended by the District in connection with the exercise of its rights hereunder shall accrue interest from the date expended until paid to the District at the maximum legal rate.  The District may retain or withhold any such amounts from the Contract Price.  If the Contractor is ordered to replace any faulty workmanship or defective materials pursuant to Paragraph (b) above, the Contractor shall replace the same with new work or materials approved by the Architect and the District, and, at its own cost, shall repair or replace, in a manner and to the extent the Architect and the District shall direct, all work or material that is damaged, injured or destroyed by the removal of said faulty workmanship or defective material, or by the replacement of the same with acceptable work or materials.  In no event shall anything in this Paragraph be deemed to constitute a waiver by the District of any other rights or remedies that it may have at law or in equity, it being acknowledged and agreed by the Contractor that the remedies set forth in this Paragraph are in addition to, and not in lieu of, any other rights or remedies that the District may have at law or in equity.

- MISCELLANEOUS

  - Prohibited Interests.  No official of the District who is authorized in such capacity and on behalf of the District to negotiate, make, accept, or approve, or to take part in negotiating, making, accepting or approving any architectural, engineering, inspection, construction or material supply contract or any subcontract in connection with construction of the Project, shall become directly or indirectly interested financially in the Project or in any part thereof.  No officer, employee, architect, attorney, engineer or inspector of or for the District who is authorized in such capacity and on behalf of the District to exercise any executive, supervisory or other similar functions in connection with construction of Project shall become directly or indirectly interested financially in this Project or in any part thereof.  The Contractor shall receive no compensation and shall repay the District for any compensation received by the Contractor under the Agreement, should the Contractor aid, abet or knowingly participate in violation of this Section 23.1.

  - Notice of Taxable Possessory Interest.  The terms of the Agreement may result in the creation of a possessory interest.  If such a possessory interest is vested in a private party to the Agreement,  the private party may be subjected to the payment of property taxes levied on such interest.

  - Assignment of Antitrust Actions.  Public Contract Code Section 7103.5 provides:

In entering into a public works contract or a subcontract to supply goods, services, or materials pursuant to a public works contract, the contractor or subcontractor offers and agrees to assign to the awarding body (the District) all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Section 15) or under the Cartwright Act (Chapter 2 (commencing with Section 16700) of Part 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, services, or materials pursuant to the public works contract or the subcontract.  This assignment shall be made and become effective at the time the awarding body tenders final payment to the contractor, without further acknowledgment by the parties.

The Contractor, for itself and all subcontractors, agrees to assign to the District all rights, title, and interest in and to all such causes of action the Contractor and all Subcontractors may have under the Agreement.  This assignment shall become effective at the time the District tenders final payment to the Contractor, and the Contractor shall require assignments from all subcontractors to comply herewith.

  - Occupancy.  The District reserves the right to occupy buildings and/or portions of the site at any time before completion, and such occupancy shall not constitute final acceptance of any part of the Work covered by the Agreement, nor shall such occupancy extend the date specified for completion of the Work.  Beneficial occupancy of building(s) does not commence any warranty period nor shall it entitle the Contractor to any additional compensation due to such occupancy.

  - Patents, Royalties and Indemnities.  The Contractor shall hold and save the District and its School Board, officers, agents, and employees harmless from liability of any nature or kind, including cost and expense, for or on account of any patented or unpatented invention, process, article, or appliance manufactured or used in the performance of the Agreement, including its use by the District, unless otherwise specifically provided in the Project Documents, and unless such liability arises from the sole negligence, or active negligence, or willful misconduct of the District.

  - Non-Discrimination.  In the performance of the terms of the Agreement, the Contractor agrees that it will not engage in nor permit such subcontractor as it may employ to engage in unlawful discrimination in employment of persons because of the race, religious creed, color, national origin, ancestry, physical handicap, medical condition, marital status, or sex of such persons.

  - Excise Taxes.  If under federal excise tax law any transaction hereunder constitutes a sale on which a federal excise tax is imposed and the sale is exempt from such excise tax because it is a sale to a state or local government for its exclusive use, the District, upon request, will execute documents necessary to show (1) that the District is a political subdivision of the State for the purposes of such exemption and (2) that the sale is for the exclusive use of the District.  No excise tax for such materials shall be included in any bid price.

  - No Assignment.  The Contractor shall not assign, transfer, convey, sublet or otherwise dispose of the Agreement or of its rights, title or interest in or to the same or any part thereof.  If the Contractor shall assign, transfer, convey, sublet or otherwise dispose of the Agreement or its right, title or interest therein, or any part thereof, such attempted or purported assignment, transfer, conveyance, sublease or other disposition shall be null, void and of no legal effect whatsoever; and the Agreement may, at the option of the District, be terminated, revoked and annulled, and the District shall thereupon be relieved and discharged from any and all liability and obligations growing out of the same to the Contractor, and to its purported assignee or transferee.

  - Notice.  All written notices required to be given pursuant to the Agreement and these General Conditions shall be either (a) personally delivered, (b) deposited in the United States express mail or first class mail, registered or certified, return receipt requested, postage prepaid, (c) delivered by overnight courier service, or (d) delivered by facsimile or e-mail transmission, provided that the original of such facsimile notice, or a copy of such e-mail notice, is sent by certified U.S. mail, postage prepaid, no later than one business day following such facsimile or e-mail transmission.  All such notices shall be deemed delivered upon actual receipt (or upon the first attempt at delivery pursuant to the methods specified in clauses (a), (b) or (c) above if the intended recipient refuses to accept delivery).  All notices to the Contractor shall be delivered to the addresses specified in the Bid Form, or to such other address as the Contractor may from time to time specify by written notice to the District:  All notices to the District shall be delivered to the Construction Manager (with a copy to the District at the address shown as the “place of bid receipt” on the Notice Calling for Bids), or to such other address as the District may from time to time specify by written notice to the Contractor.

  - No Waiver.  The failure of the District in any one or more instances to insist upon strict performance of any of the terms of the Agreement or to exercise any option herein conferred shall not be construed as a waiver or relinquishment to any extent of the right to assert or rely upon any such terms or option on any future occasion.

  - No Oral Agreements.  No oral agreement or conversation with any officer, agent, or employee of the District, either before or after the execution of the Contract, shall affect or modify any of the terms or obligations contained in any of the document comprising the Contract.

  - Time is of the Essence.  Time is of the essence of every provision contained in the Agreement an in these General Conditions.

  - Indemnification.  Contractor.  Contractor shall defend, indemnify and hold harmless the District and others as indicated in Section 00500 – Agreement and as indicated herein. Contractor shall ensure that its contract with each of its subcontractors contains provisions requiring the subcontractors to defend, indemnify and hold harmless the District, and others as indicated in Section 00500 – Agreement, as indicated here and consistent with the language of 3.15.1.

## END OF SECTION