PAYMENT PROCEDURES

# PART 1 - GENERAL

1.1	SUMMARY

A.	This Section specifies administrative and procedural requirements governing the Contractor's Applications for Payment.

B.	Submit applications for payment to Construction Manager in accordance with the schedule established by the conditions of the Contract and Agreement between Owner and Contractor.

C.	The Contractor's Construction Schedule and Submittal Schedule are included in Section "Submittals".

D.	The Contractor agrees to provide an updated certified “As-Built” with every pay application both “Hard Copy” and electronic copy that is approved by the Engineer, Inspector of Record, and the Construction Manager.

1.2	SCHEDULE OF VALUES

A.	Coordinate preparation of the Schedule of Values with preparation of the Contractor's Construction Schedule.

1.	Submit the Schedule of Values to the Construction Manager at the earliest feasible date, but in no case later than 7 days before the date scheduled for submittal of the initial Application for Payment.

B.	Format and Content:  Use the Project Manual Table of Contents as a guide to establish the format for the Schedule of Values.

1.	Identification:  Include the following Project identification on the Schedule of Values:

a.	Project name and location.

b.	Name of the Engineer.

c.	Project number.

d.	Contractor's name and address.

e.	Date of submittal.

2.	Arrange the Schedule of Values in a tabular form with separate columns to indicate the following for each item listed:

a.	Generic name.

b.	Related Specification Section.

c.	Name of subcontractor.

d.	Dollar value.

e.	Percentage of Contract Sum to the nearest one-hundredth percent, adjusted to total 100 percent.

3.	Provide a breakdown of the Contract Sum in sufficient detail to facilitate continued evaluation of Applications for Payment and progress reports.  Break principal subcontract amounts down into specific line items.

4.	Round amounts off to the nearest whole dollar; the total shall equal the Contract Sum.

5.	For each part of the Work where an Application for Payment may include materials or equipment, purchased or fabricated and stored, but not yet installed, provide separate line items on the Schedule of Values for initial cost of the materials, for each subsequent stage of completion, and for total installed value of that part of the Work.

6.	Schedule Updating:  Update and resubmit the Schedule of Values when Change Orders or Construction Change Directives result in a change in the Contract Sum.

1.3	APPLICATIONS FOR PAYMENT:

A.	Each Application for Payment shall be consistent with previous applications and payments as certified by the Engineer and paid for by the School District.

B.	Payment Application Times:  Each progress payment date is as indicated in the Agreement.  The period of construction Work covered by each Application or Payment is the period indicated in the Agreement.

C.	Payment Application Forms:  Use AIA Document G702 and Continuation Sheets G 703 as the form for Application for Payment.

D.	Application Preparation:  Complete every entry on the form, including notarization and execution by person authorized to sign legal documents on behalf of the District.  Incomplete applications will be returned without action.

1.	Entries shall match data on the Schedule of Values and Contractor's Construction Schedule.  Use updated schedules if revisions have been made.

2.	Include amounts of Change Orders and Construction Change Directives issued prior to the last day of the construction period covered by the application.

3.	Transmit each copy with a transmittal form listing attachments, and recording appropriate information related to the application in a manner acceptable to the Engineer and Construction Manager.

4.	When the Engineer finds the application completed and correct will transmit a certificate for payment to Owner with a copy to the Contractor.

E.	Lien Releases:  With each Application for Payment submit Lien Releases from subcontractors or sub- subcontractors and suppliers for the construction period covered by the previous application.

1.	Submit partial Lien Releases on each item for the amount requested, prior to deduction for retainage, on each item.

2.	When an application shows completion of an item, submit final or full Lien Releases.

a.	Submit final Application for Payment with or preceded by final Releases from every entity involved with performance of Work covered by the application that could lawfully be entitled to a lien.

3.	Waiver Forms:  Submit waivers of lien on forms, and executed in a manner, acceptable to the District.

F.	Initial Application for Payment:  Administrative actions and submittals that must precede or coincide with submittal of the first Application for Payment include the following:

1.	List of subcontractors.

2.	Schedule of Values.

3.	Contractor's Construction Schedule (preliminary if not final).

4.	Copies of authorizations and licenses from governing authorities for performance of the Work.

5.	Certificates of insurance and insurance policies.

6.	Performance and payment bonds (if required).

G.	Application for Payment at Substantial Completion:  Following issuance of the Certificate of Substantial Completion, submit an Application for Payment; this application shall reflect any Certificates of Partial Substantial Completion issued previously for District occupancy of designated portions of the Work.

1.	Administrative actions and submittals that shall proceed or coincide with this application include:

a.	Project inspector's status of completion report.

b.	Warranties (guarantees) and maintenance agreements.

c.	Test/adjust/balance records.

d.	Maintenance instructions.

e.	Meter readings.

f.	Start-up performance reports.

g.	Change-over information related to Owner's occupancy, use, operation and maintenance.

h.	Final cleaning.

i.	Application for reduction of retainage, and consent of surety.

j.	List of incomplete Work, recognized as exceptions to Architect's Certificate of Substantial Completion.

H.	Final Payment Application:  Administrative actions and submittals that must precede or coincide with submittal of the final payment Application for Payment include the following:

1.	Completion of Project closeout requirements.

2.	Completion of items specified for completion after Substantial Completion.

3.	Assurance that unsettled claims will be settled.

4.	Assurance that Work not complete and accepted will be completed without undue delay.

5.	Transmittal of required Project construction records to Owner.

6.	Removal of temporary facilities and services.

7.	Removal of surplus materials, rubbish and similar elements.

8.	Submit the final complete “As-builts” both hard copy and electronic copies with proper electronic titles for each page.

PART 2 – PRODUCTS - (Not Applicable)

PART 3 – EXECUTION - (Not Applicable)

END OF SECTION